Choosing and using an Estimating Approach
Technique Paper (TP)
© Copyright International Business Machines Corporation 1998, 2014
All Rights Reserved
Version 1.2, June 2007

Description
Purpose
The purpose of this document is to help you choose and use appropriate estimating approaches when carrying out an estimate.
There are 7 approaches outlined in this document 2 of which describe typical specialist estimating tools.
The approaches are aimed at supporting the creation of estimates in software development; however, most of the listed approaches may be tailored to work with virtually any type of project.
The paper should be read by anyone who is required to create an estimate, e.g. Project Managers, IT Architects, Business Analysts and others. Note that the words Estimating and Estimation are used interchangeably, to mean the same thing.
Usage Context
This document describes the preparation of a cost estimate prior to starting the delivery of a project. The cost estimate may be an input to pricing. In the diagram below the approaches described in this document are within the Estimate box. Pricing will be carried out based on the estimated cost. Both Price and Schedule will be presented to the customer. Any rejection of these by the customer will trigger re-estimation from the Start box.

Start
Size/Scope
Effort
Schedule
Resource
Cost

Risk Contin-
gency
Reqd GP
Price
Budget

CUSTOMER

Estimate
Price
Win Strat

Contingency

Figure 1. Estimation and Pricing Cycle

The point in the project lifecycle when you create the estimate will affect the approach you are able to take. When you need to estimate changes to a project during its life, these same approaches can be used to determine the impact (to schedules, effort or cost) of the change request.
To make effective use of this paper, you must have undertaken an extensive data collection exercise for the project you wish to estimate. In so doing you will have some indication of:
- the scope and boundaries of the application you are to build or enhance
- an indication of the technical solution proposed
- an initial quantification of scope, or size, of the project
The document does not provide information about the estimating process during project delivery.
Using this Document - Estimating Considerations
These estimating approaches are a summary of approaches that have been used successfully for projects within IBM and the IT industry generally.
1. Estimating by Analogy
2. Deadline Driven Approach
3. Parametric Approach
4. Estimating using Artifact counts and Work Distribution Models
5. Plan Driven (Bottom Up) Estimating
6. Plan driven Estimating tools
7. Parametric size driven tools
No approach is BEST. The choice of approach depends on project type, existing documentation and available inputs.
Never use only one approach. An estimate must be cross-referenced using at least two approaches -three is even better.
Each suggested approach has a number of variations and techniques, with some techniques being used within more than one approach. In many cases designing a combined approach will be necessary. The approaches identified are generic and should be used as guidance. In addition to the listed approaches, always look for specific advice, recommendations and mandated approaches from your business areas.
Many of the approaches have supporting tools, models or templates; others are based around generic tool types. The approaches listed are not prescriptive, nor exhaustive. Not all steps in a chosen approach need be completed. E.g. if only effort is required, you may curtail steps which focus on schedule or cost information to the extent that the effort estimate is complete – although in this case care should be taken to ensure that schedule considerations do not affect effort, as it normally does.
Tools, Models, Templates and Techniques
In this document the term ‘tool’ is restricted to a software application specifically developed for the creation of project estimates, and which usually costs money. The major factor which distinguishes a tool from a model/template is that a tool is calibrated based on historical data or recognizable algorithms[1].
[1] Note: There is a difference between specialist Estimating tools and Scheduling tools. The former usually have built in project metrics and algorithmic intelligence to enable effort, cost AND base schedule to be assessed, usually with built in do-ability checks. Scheduling tools (e.g. RPM and MS Project) have no built in metrics or effort/cost intelligence. Note: Scheduling tools are very useful in obtaining do-able schedules from approximate schedules based on estimating tool output. There are moves to combine these tools but the industry has not yet succeeded (Q4 2006).
Tools can make estimating quick and easy, but the ‘black box’ nature of tools leads to lack of confidence in the results. Therefore tools should be used initially as a validation technique. However comparison of actuals with tool output over a number of projects can lead to extended reliance and confidence in tool output.
To overcome the ‘black box’ nature of tools, many estimators have developed their own models:
Whenever you are thinking of building a new spreadsheet you should research existing models and/or ask your local estimating Subject Matter Expert for advice on existing intellectual capital.
Your organisation may have approaches, including specialist tools and techniques, for a given technology or architecture. You should research existing documentation within your organization and with specialists to determine if this exists. You should always contact your estimating subject matter expert to seek advice on appropriate tools, models and templates.
The term estimating model is used where an approach is supported by a template requiring both calibration and estimating input from your project before it is useful. (Calibration is often done by ‘asking the expert’ rather than the more appropriate method of gathering and analyzing historical data). Many models and templates have been built by practitioners over the years and are usually in the form of spreadsheets.
Techniques refer to the specific mechanism for undertaking an estimating activity or task. For instance, to assess the confidence level or variance of any estimate, the ‘wide band Delphi’ technique, or ‘Monte Carlo analysis’ technique can be used.
The Top-down estimating technique assesses overall project size in some appropriate unit, and converts this size into a cost (and schedule) using algorithms, historical information or rules of thumb. The process can end at this point with a first assessment of effort, cost and schedule. Many tools however take this effort figure and, via in built algorithms, allocate fractions of this total effort to different phases, activities, tasks or work products to be undertaken or delivered by the project. From this a more detailed project schedule can be generated.
The Bottom-up estimating technique assesses effort figures for individual elements of the project e.g., activities, tasks or work products. The technique then sums up these individual effort figures to provide an overall project effort (and thus cost). Effort figures for the individual elements are best obtained from historical data. The technique relies on having a set of elements available and these are often provided by engagement models, templates and so on, or from past project plans.
These two techniques may be used in many different approaches and are often quoted as alternative methods of estimating. Each has its own advocates and both have tools which attempt to automate them. However, the best strategy when creating an estimate is to select approaches which involve both top-down and bottom-up techniques where possible. Commonly a top down approach is used to validate a bottom up approach.
Techniques are usually more general than approaches. Typing the name of a technique into an Internet search engine will provide information on how to undertake the technique.
Non-Linearity
Analysis of the software industry over its life time has shown that there is a relationship between size, effort and schedule and that this relationship is non-linear. This means that doubling the size of the project does NOT simply double the effort but increases it greater than 2-fold. Similarly when compressing the schedule we also increase the effort (and therefore cost)
These effects should always be taken into account when converting effort to schedule or assessing effort from size.
Aspects of this non-linearity are discussed in the Rules of Thumb document (on the estimating wiki). Putnam uses his ‘software equation’ within the SLIM estimating tool to relate these factors, and CoCoMo II has similar factors built into the algorithms used in the CoCoMo toolset.
Confidence Levels (Estimate Vaiance)
Estimates should always be produced with a level of confidence attached. This is usually expressed as a % Certainty, e.g.:
The estimate is 90% certain of being under $1,000,000.
OR
By providing a High, Expected and Low value for the estimate, e.g.:
The estimate has a range from$ 600K to $1.1M with an expected (nominal) l value of $800,000.
See the technique paper Estimation with Variance for techniques on assessing confidence levels.
Best Practice Considerations
1. As you step through any approach make sure you know the provenance (where it came from) and content of all the input variables (e.g. if using productivity figures, is it just builds productivity or full lifecycle?). This will improve confidence in the estimate values.
2. Always list your assumptions, so that the basis of your estimate is clear and transparent, both now and to subsequent readers (including yourself).
3. Always use more than one approach so that you can ‘validate’ your estimate by showing a similar estimate value from a different approach
4. Always estimate the variance (confidence level) of the output of the estimating process, so that the audience for the estimate has some idea of the level of accuracy being presented. See ‘Estimating with Variance’ Technique Paper for details.
See also related documents below.
What do we mean by Size
In the world of software development, size means different things to different groups of people, for instance a software developer compared to the Sponsor. So the answer to the question “How big is the project?” might be:
"I believe that this is about a 500 effort-hour project." Or “About 200 screens” or “Approximately £200,000 pounds” or “Nearly 2000 Function Points”.
IN THIS DOCUMENT SIZE DOES NOT MEAN EFFORT OR COST
To the software estimator size quantifies what a project delivers or proposes to deliver. Size implies parametric counts such as source lines of code or function points, or counts of delivered artifacts (screens, etc). These are also the size units needed for use in most estimating tools.
IN THIS DOCUMENT SIZE REFERS TO PARAMETRIC or ARTEFACT COUNT SIZE

Content
Estimation Strategy
An estimating strategy requires you to decide:
1. What the final goal of the estimating activities will be? - from indicative cost only to fully priced offer to the client.
2. Which tools, models, templates and techniques to use to create your estimate?
3. Which approaches to use to deliver your estimate against your goal?
4. How you will handle the results of each approach?
For example, you may be most confident with one approach (primary) and use another approach (secondary) to validate the first approach – that is, demonstrate confidence in the primary approach by demonstrating that the secondary approach gives a similar result.
Alternatively, you may decide to continue iterating around your estimating approaches until the outputs are within a certain target percentage of each other. You could then use the average of the two approaches as your baseline estimate.
Document your estimation strategy along with your estimate, so it is clear to your colleagues, and for use at any estimating reviews that may be held.
The rest of this document describes the approaches that you might consider within your estimation strategy.
Choosing Your Approach
It is recommended that you review the approaches listed in this section and choose the best approaches or combination of approaches for your project. For ease of reference, each approach starts on a new page.
Steps to choosing which approaches to use:
1. Review the available project documentation
2. Review the recommended or mandated estimating approach required by your business area, which may include tools, models, templates and/or techniques
3. Review the list of approaches described in this document.
4. Identify the approaches (at least 2) you will use based on the above business requirements and level of knowledge from the project documentation.
These approaches should be used in conjunction with the Estimating Considerations Checklist Work Product.
Approach summary
Approach	Notes
Analogy	Indicative only – gives a rough Order of magnitude - not for contractual basis – always use for validation
Plan-driven estimation (bottom-up) / VARIANT / Plan Driven Estimation TOOL	Use whenever possible – likely to be the most accurate approach when available. / [Always to use an appropriate tool, if available, when choosing this approach].
Parametric Size / VARIANT / Size Based Estimation TOOL	Top-down validation approach, variance tends to be large. / Experience, historical data and use of tools can make this a candidate for the primary estimation approach. / [Try to use an appropriate tool, if available, when choosing this approach].
Artifact and work distribution / VARIANT / Size Based Estimation TOOL	Usually used to provide indicative ballpark estimate for budgetary purposes only. / Experience, historical data and use of tools can make this a candidate for the primary estimation approach. / [Try to use an appropriate tool, if available, when choosing this approach].
Deadline-driven estimation	Not recommended – must be validated by other approaches, best used to indicate that a project is not do-able or that scope reduction is required.

1. Analogy
When to choose this approach
Always use this approach as a validation technique to one or more of the other approaches – may be used as primary approach if no other approach is feasible. Indicative only – gives a rough Order of magnitude - not for contractual basis.
Input Requirements
The effort (schedule, resources etc) actuals experienced by completed projects of a similar nature / scope / size / complexity and solution.
Make use of any historical data repository available, or you may have personal experience. You can obtain help getting such data from your estimating SME.
A size / complexity comparison between your project and those in the historical repository.
Size may be in the form of Function Points, Lines of code or delivered artifacts such as screens, reports, interfaces. Technical deliverables specific to the proposed solution are often used.
Steps when carrying out the approach
1. Assemble all knowledge, documentation and data on the request/project.
2. Use historical data and expert knowledge to identify past projects similar to the one being estimated.
3. Note the effort and schedule for the historical project(s) for the phase(s) under consideration - you must understand the ‘content’ of the data, for example, is it for technical effort only or all effort?
A range (Hi, Expected, Lo) of Effort / Cost / Schedule should be the goal. Use Wide band Delphi or Monte Carlo techniques to assess this range.
1. Adjust the effort and schedule for your project against the historical data by assessing size, complexity and other differentiators (for example, if your project is twice the size of the historical one, your estimate is likely to be at least twice the effort/cost)
2. Convert to monetary cost if required
3. Add additional costs such as hardware, critical computer resources etc (see Estimating Considerations Checklist Work Product)
4. Use Wide band Delphi or Monte Carlo techniques to assess this range.
5. Assess whether the approach worked satisfactorily
Typical Sources of Error
This is, by its very nature, an inaccurate estimation method and should be used only as a validation technique, or when NO OTHER METHOD is available. Some specific areas which cause inaccuracies are:
- Lack of historical data means poor choice of projects for comparison
- Inability to assess size from the available historical data
Using the Output
The output might be for effort, cost, schedule depending on your requirements and the availability of appropriate historical data.
The output will be only an indication of the effort, schedule and/or resources required by your project. Use for validation purposes only.
Plan Driven Estimation (Bottom Up)
When to choose this approach
This approach should be used whenever possible; it is likely to be the most accurate estimate. If you have a work breakdown structure available, you should use this approach.
It is most commonly used in conjunction with a scheduling tool and an existing ‘default’ PBS/WBS/Schedule. You should rarely consider crating this manually from scratch.
Input Requirements
1. Detailed Product Breakdown structure / Work Breakdown Structure / Task schedule.
2. Estimates for individual work products (or activities/tasks).
3. Size of project compared to default values (if they are known/given)
Steps when carrying out the approach
1. Assemble all knowledge, documentation and data on the request/project
2. Use historical data, expert knowledge or templates of project types / Engagement models to obtain a Work Breakdown Structure representing ALL work products/activities or tasks to be carried out.
- Engagement Support Environment (ESE) tool can supply default WBSs. This is likely to be replaced in 2007/8 with Rational Method Composer (RMC).
- The WBS should be entered into a scheduling tool such as RPM or MS Project
- This may be for a single project phase or the whole project
1. Tailor the model/plan to reflect the work products/activities/tasks appropriate to your project (consider additions and deletions – sometimes referred to as a Method Adoption Workshop and can be done in ESE or RMC)
2. Manually set the effort required by each work product/activity/task, and the dependencies between them, within the schedule (if default values then confirm they are appropriate)
- Adjust your project effort for each work product/activity/task against any existing (default) values, based on size difference. This will require comparison of size and complexity of the project against those default values.
- Use an experienced person or (better) historical data to assess work product/activity/task effort.
1. For each work product/activity/task, allocate the required resources (number and specialization)
2. Determine the overall effort and schedule after resourcing for the completion of all work products
This should be automatically provided by the scheduler.
Add effort/cost associated with resource leveling, non productive hours,….etc
Can be automated – but make sure the results of automatic resource leveling are realistic.
Use historical data, expert knowledge, work distribution models to define the effort for any other project phases if not included yet.
- Use your historical data
- Or, if not available, see rules of thumb for this kind of data
Review the overall effort and the schedule to confirm the project is do-able.
  1. If the schedule and effort differ markedly from the square root rule (see Rules of Thumb document on the wiki) then you should consider the project as not do-able in its present form.
Convert to monetary cost if required
  1. If rates are in the tool this will be automatically generated.
1. Add additional costs such as hardware, critical computer resources
2. Use Wide band Delphi or Monte Carlo techniques to assess confidence levels and variance
Scheduling tool add-ins are available for Monte Carlo analysis.
Assess whether the approach worked satisfactorily
Typical Sources of Error
The bottom up process has weaknesses which should be addressed when undertaking such an estimate. Some of these weaknesses are outlined below.
- It underestimates the overhead required and the non-software tasks associated with a larger project, often dramatically.
- Bottom-up estimating cannot be done effectively early in the project life cycle when bid/no bid or go/no go decisions are made and money, time, and staff are allocated to the effort. There is simply insufficient detail to determine all of the software elements, much less the project elements.
- It ignores the impact on schedule and effort of different sized teams. Schedule is simply effort divided by staff.
- It does not account for the non-linear impacts of time, cost, and quality constraints.
- It is not suitable for rapid, cost-effective, what-if analysis.
Sources of Information
Existing WBS templates in GS Method by engagement model. (see also comment earlier on RMC)
Using the Output
The output is an estimate for effort, cost and schedule which is usually the most accurate estimate available, but is also the most time consuming to develop.
Parametric
When to choose this approach
Use this approach when you want an indicative (ballpark) estimate for budgetary purposes, or need to validate estimates from other approaches. (See also Approach 7 – Size based estimation tools.)
Input Requirements
Size of the project to be undertaken, - overall project size has been assessed using a single parameter, e.g.:
Function Point Count, Line of code count, number of use cases …etc
This is not an exhaustive list – review the technique to decide if other parametrics are appropriate in your case.
An indication of the productivity of delivering the chosen parameter.
E.g. 1. Function Point Productivity will be 10 Hours per Function Point
E.g. 2. Effort for a 20 Use Case project is 4,000 hours so productivity will be 200 hrs per Use Case.
Steps when carrying out the approach
1. Assemble all knowledge, documentation and data on the request/project
2. Confirm the size of the project based on the defined scope, using your chosen sizing parameter(s)
  1. You should ask the advice of an experienced person or expert to help with this.
3. Assess the typical productivity of the sizing units, adjusting for your unique project attributes
COCOMO II can provide effort adjustment information. See: COCOMO web site.
1. Convert productivity and size into effort
  1. Effort = Productivity * Size (example only, your equation may be different)
2. Add any additional effort not included in above
  1. See ‘Estimation Consideration Checklist’ for suggested omissions
3. Convert effort into elapsed schedule
  1. using rules of thumb or historical data
  2. If your objective is a PBS/WBS (as is likely if you are to commit to this estimate) you must use a scheduling tool and allocate effort against each WBS element, create dependencies and allocate resources. Some tools supply ‘default’ schedules or you can use one you have used before. Other tools populate WBS with effort and schedule for you.
4. Add effort/cost associated with resource levelling, non productive hours, manpower rates [2]…..
  [2] It may require iteration around steps 6 and 7 (or even a review of scope) to create a viable schedule against the assessed effort.
  1. With a WBS/PBS in a tool, resource levelling can be done automatically; but use automation with caution and ALWAYS review output against common sense.
  2. With no WBS make assumptions about additional effort requirements (e.g. 10% added to cover holidays, training, resource levelling (see rules of thumb on wiki for more advice))
5. Convert to monetary cost if required
  1. Blended rate per hour * total hours OR
  2. Resource costs by role from a WBS/PBS resourced schedule
6. Add additional costs such as hardware, critical computer resources
7. Use Wide band Delphi or Monte Carlo techniques to assess confidence levels and variance
8. Assess whether the approach worked satisfactorily
Typical Sources of Error
- Inaccurate size assessment (particularly Lines of Code)
- Productivity figures not based on ‘real’ data
- Beware the impact on schedule and effort of different sized teams. Large teams, more effort.
- There is a tendency to ignore non linearity in any schedule compression.
Sources of Information.
There is a template available on the tools page of the estimating wiki. The ROM Estimator model[3] uses function Point size and the Use Case Estimating Worksheet (UCEW)[4] uses ‘count of use cases’ size.
[3] This is an excel spreadsheet version – use as a template model and you must populate with your own data.
[4] This is a actual estimation tool used ‘in anger’ within IBM on a number of engagements.
Using the Output
The output should be considered as indicative only.
Improving this approach, based on additional data could improve accuracy such that it can be used as the primary estimation approach with validation via other approaches.
If a WBS has been created it can form the basis of a template WBS for input to other approaches.
Artifact and Work Distribution
When to choose this approach
Use this approach when you want an indicative (ballpark) estimate for budgetary purposes, or need to validate estimates from other approaches. (See also Approach 7 – Size based estimation tools.)
Input Requirements
Size of project, as a count of artifacts. Artifacts may be categorized as low, average and high complexity
  1. E.g. The project will deliver 20 low complexity screens and 10 medium complexity screens …….etc
An indication of the effort per artifact by complexity is available
  1. E.g. A complex screen takes 7 days to build and unit test a medium screen …….. etc
An indication of the effort profile across phases/iterations within the project.
  1. E.g. Solution Outline 10%, Macro Design 15%, Micro Design 35%, Build 30%, Deploy 10%,
Steps when carrying out the approach
1. Assemble all knowledge, documentation and data on the request/project
2. Confirm the count of the artifacts
  1. Define the artifact(s) which you will deliver on the project
  2. Define and assess complexity levels for each artifact type
  3. Count the number of each artefact by complexity
3. Assess the build effort for each artefact by complexity
Use historical data (best) and expert knowledge to define the effort to build the required artifacts by complexity
1. Sum the build effort for the count of all artifacts to provide an overall build effort
2. Assess the Effort for all the ‘non build’ project phases / activities
  1. Use historical data, expert knowledge, work distribution models, rules of thumb
  2. Estimation Considerations checklist has a list of items you should consider.
3. Convert effort into elapsed schedule
  1. using rules of thumb or historical data
  2. If your objective is a PBS/WBS (as is likely if you are to commit to this estimate) you must use a scheduling tool and allocate effort against each WBS element, create dependencies and allocate resources. Some tools supply ‘default’ schedules or you can use one you have used before.
4. Add effort/cost associated with resource levelling, non productive hours, manpower rates [5]…..
  [5] It may require iteration around steps 6 and 7 (or even a review of scope) to create a viable schedule against the assessed effort.
  1. With a PBS/ WBS in a tool, resource levelling can be done automatically; but use automation with caution and ALWAYS review output against common sense.
  2. With no PBS/WBS make assumptions about additional effort requirements (e.g. 10% added to cover holidays, training, resource levelling (see rules of thumb on wiki for more advice))
5. Convert to monetary cost if required
  1. Blended rate per hour * total hours OR
  2. Resource costs by role from a WBS/PBS resourced schedule …….
6. Add additional costs such as hardware, critical computer resources
7. Use Wide band Delphi or Monte Carlo techniques to assess confidence levels and variance
8. Assess whether the approach worked satisfactorily
Typical Sources of Error
- Inaccurate counts of artefacts.
- Artefact effort and/or work distribution models not based on historical data
- It can underestimate the overhead required and the non-software tasks associated with a larger project, often dramatically.
- It can ignore the impact on schedule and effort of different sized teams. Large teams, more effort.
- It does not account for the non-linear impacts of time, cost, and quality constraints.
Sources of Information
There is a template for this on the tools page of the estimating wiki called the Top Down estimator[6]. This contains detailed instructions on artifact based method.
[6] This is a model rather than a tool and needs user data to calibrate.
Using the Output
The output should be used as indicative only unless confidence levels are acceptable.
This estimate can be used as the primary estimation approach with validation via other approaches.
If a WBS has been created it can form the basis of a template WBS for input to other approaches.
Deadline-driven Estimating
When to choose this approach
It is recommended that you do not use this approach. It should be considered only if you have essential deadlines which must be achieved. It must be validated by other approaches and is best used to indicate that a project cannot be done in the timescale, or that scope reduction is required.
Input Requirements
1. The set deadline date(s)
2. An appropriate work breakdown structure, obtained from historical data, templates from your past or from another approach or tool.
3. An idea of the size of the project
Steps when carrying out the approach
1. Assemble all knowledge, documentation and data on the request/project.
2. Use historical data, expert knowledge or templates of past projects to create a Work Breakdown Structure representing ALL Work Products (or activities or tasks) to be carried out.
   This should be entered into a scheduling tool such as MS Project or RPM
3. Estimate the effort required for each task; this will depend on getting an initial effort, size and complexity of the project activities and you can easily underestimate here.
   This will give you the total effort required.
4. Define the dependencies between tasks within the schedule if not done already.
5. Enter the overall Resources for completion of all the tasks; 1,2 or 3 people etc
6. Run the tool to schedule the project based on the finish date deadline.
7. For each activity / task, adjust the required resources (number and specialisation) for each one in order for the start date to be today or in the future.
8. Add effort/cost associated with resource leveling, non productive hours and so on, and repeat step 7. Beware the non linear nature of schedule compression - cross check using the square root rule; that is Sqrt (effort months) = elapsed months = total FTE
9. Review the overall effort and the required schedule to confirm that the project can be done in the timescale. If the schedule and effort differ markedly from the square root rule then you should consider the project impossible in its present form.
Look at historical projects to confirm if the that schedule with that effort is achievable, consider de-scoping, revisit the assumptions etc
1. Use historical data, expert knowledge and work distribution models to define the effort for any other project phases if not included. See rules of thumb for this kind of data (or better still use your historical data).
2. Convert to monetary cost if required
3. Add additional costs such as hardware, critical computer resources
4. Use Wide band Delphi or Monte Carlo techniques to assess confidence levels and variance
5. Assess whether the approach worked satisfactorily
Typical Sources of Error
The deadline driven process has major weaknesses which should be addressed when undertaking such an estimate. Some of these weaknesses are addressed below.
- It often underestimates the overhead required and the non-software tasks associated with a larger project, often dramatically.
- It ignores the impact on schedule and effort of different sized teams. Schedule is simply effort divided by staff.
- It does not account for the non-linear impacts of time, cost, and quality constraints.
- It is not suitable for rapid, cost-effective, what-if analysis.
- It is commonly used to shoehorn an impossible schedule or effort requirement into an apparently do-able plan.
Using the Output
If it is not possible to do this project at step 9 then you must reduce scope until it becomes feasible. This is potentially the most ‘dangerous’ approach as it makes assumptions about the ability to hit a deadline which is a desired outcome and the temptation is to massage the schedule until it fits.
Always compare the output of this approach with that from at least one other approach. Given the inherent risk in this approach, comparing to two others would be better.

Estimating Tools
Estimating tools are usually developed by third parties and available at a price from vendors. Some tools are available from IBM sources, viz:
- Use Case Estimating tool (stand-alone tool from Estimating experts in IBM Canada). Available from the estimating wiki tools page. (Item entitled UCEW)
- LEAD (Part of the ESE toolset, but limited to CAD and E Business engagement models and soon to be phased out (October 2006)
- Rational Project Estimator (same as Ascendant Summit) -No longer supported (August 2006)
There are basically two types of tool:
- Ones which uses default WBS/Activity/Task list with default effort, schedules and dependencies. In this doc they are called ‘Plan Driven’ tools. They are basically automating a bottom iup aproach.
- Ones which use an overall project size and allocate effort, then allocate this to phases/schedules based on an appropriate WBS or plan. In this doc they are called ‘Size Driven’ tools. This is a top down approach.
The latest tools may contain elements of both these types. The generic approaches associated with these 2 tool types is described in the rest of this section.
Plan Driven Estimation via a Tool.
When to choose this approach
This is an automated version of the Plan Driven Estimation (Bottom Up) described above.
This approach requires a tool such as Ascendant Summit or Rational Project Estimator or a tool developed by/for your business area.
With local historical data for formal recalibration, these tools can become the primary estimation approach.
Methods of use vary by tool but in general this type of tool has a range of effort associated with each task / work product. Your inputs will drive the choice of which part of this range (low, average or high) the tool uses when doing the estimate.
Input Requirements
1. Size of project, in estimating factors, supported by the tool.
2. Mapping of your project type to one available within the tool
Steps when carrying out the approach
1. Assemble all knowledge, documentation and data on the request/project
2. Select an appropriate engagement model / project type / within the tool
One which most closely resembles your project work product set
This often generates a base estimate for the default model, complexity and size
Assess the size/complexity of your project against the chosen model
This often requires you to assess your project against the estimating drivers (sometimes called estimating factors) within the tool
Input this size/complexity into the tool
- This will usually generate an estimate based on your current choices
- The estimate is allocated at the work product / task level
- There are often additional inputs required by the tool before a realistic estimate will be created. You should review the tool documentation for specifics
Create an estimate as described within the tool
If not generated automatically (see above)
1. Review the work product / task effort allocation used by the tool to confirm that it is appropriate
2. Review the estimating drivers defined within the tool and adjust to best reflect your project
3. Review each task to confirm that the effort is appropriate
4. Confirm correct cost conversion (if necessary)
5. Add additional costs (hw etc)
6. Assess the variance of the output.
This may be built into the tool or require what iffing around size and complexity.
1. Use Wide band Delphi or Monte Carlo techniques to assess confidence levels and variance of the inputs (what iffing by varying thae value of these inputs can generate Hi, Mid, Lo values for the estimate).
2. Assess whether the approach worked satisfactorily
Typical Sources of Error
Inappropriate choice of project type / engagement model
Complexity associated with adjusting effort per activity/task via estimating factors or manually.
Size and/or complexity measures vary by tool and you should confirm how the tool adjusts for size and confirm you understand and have the required data.
Sources of Information
Tool User manual.
Using the Output
Output from this type of tool is commonly used to populate scheduling tools such as MS Project, RPM etc
With a formal recalibration procedure and use of historical data this can become a primary estimation approach.
Size Driven Estimation Tool
When to choose this approach
This is an automated version of the Parameter and/or Artefact driven estimating approach described above.
This approach requires a tool such as QSM SLIM or KnowledgePlan etc, or a model or template developed by/for your business area.
With local historical data for formal recalibration, these tools can become the primary estimation approach.
Input Requirements
1. Size of project in parametric or artifacts supported by the tool.
2. Gearing factor which relates available sizing metric to tool default sizing metric.
3. Mapping of your project type to one available within the tool.
4. Productivity based on historical data (this type of tool commonly uses a default value if you cannot supply one)
Steps when carrying out the approach
1. Assemble all knowledge, documentation and data on the request/project
2. Review the required tool size input(s) and determine your ‘size’ and its confidence level
3. Select an appropriate engagement model / project type / within the tool
One which most closely resembles your project work product set
This often generates a base estimate for the default model, complexity and size
Select other required tool inputs and identify the appropriate tool input values for your project using 1 and your best judgment on other
- Usually offered via drop downs or radio buttons.
- Inputs might include staff skill levels, process maturity, technical maturity etc.
Assess the accuracy/confidence levels of the input values (included in tool sometimes but do simple sensitivity analysis (’what iffing’) on high, low and nominal values if not).
Optionally you may be able to generate a WBS/activity/task schedule based on your chosen project type and default effort/schedule values for
1. Confirm correct cost conversion (if necessary)
2. Add additional costs (hw etc)
3. Assess the variance of the output.
Some tools include confidence levels on inputs and output. Others require what iffing around size and other inputs.
Typical Sources of Error
Inappropriate choice of project type / engagement model
Complexity associated with adjusting effort per activity/task via estimating factors or manually.
Size and/or complexity measures vary by tool and you should confirm how the tool adjusts for size and confirm you understand and have the required data.
Sources of Information
Tool user manual.
Using the Output
Output from this type of tool is commonly used to provide rapid ballpark/indicative estimates for budgetary purposes.
With a formal recalibration procedure and use of historical data this can become a primary estimation approach
Key Considerations
None
References
Sources of Information
Historical data from past projects performed by your organization, your own experience or the IT industry.
BCA database
Industry
Ask your Estimating SME.
Related Documents - Where can you get more information?
Blue underlined words and phrases are hyperlinks to related documents, approach details, models, tools and techniques. Here are a few related documents, all are currently (Q4 2006) available on the estimating wiki.
Estimation Best Practice
Estimation Tool Guidelines
Estimation Tools / models / template for download (or link to home site)
Estimating Checklist
Estimating with Variance
Other Sources: Opal estimating content, GS Method content, IBM Estimating Guidance ……..ask your Estimating SME.

Revision History
Revision Number	Revision Date	Summary of Changes	Authors
Version 1.2	June 2007	Removed OPAL references
Version 1.1	Dec 2006	Initial draft	Pete Ellis