IBM Global Services
Assessing Viability
Technique Paper (TP)
© Copyright International Business Machines Corporation, 1998, 2007
All Rights Reserved
Version 3.0 February 2007
Introduction
The objective of this technique is to assist in assessing the viability of implementing an IT system. This is documented in the Viability Assessment work product.
Viability is typically re-assessed multiple times, as more information becomes available during the project lifecycle. The purpose of the technique paper is to provide additional guidance on the steps of assessing the viability of any of the following: business requirements, solution design, cutover to production and project delivery. The questions are intended to supplement those found in the Viability Assessment work product description. It is used as part of the overall process of performing a Viability Assessment. The guidance in this technique is organized in terms of four types of assessment conducted at various phases of the project:
- Assessment of the business requirements and constraints (section 1)
- Assessment of the solution design (section 2)
- Assessment of the cutover to production (section 3)
- Assessment of the project delivery (section 4)
  The document sections are best applied to the project lifecycle as shown below, however, the practitioner is encouraged to use all sections of the document they feel are relevant to the assessment.
# Assessment of Business Requirements and Constraints
The goal of this step is to assess the understanding of business requirements that pertain to the project as well as the associated acceptance / success criteria. The reviewer is looking for a current, well-articulated and approved set of business requirements linked to the system designs to guide solution development. The list below can be used for a quality assessment as a good set of business requirements will have the characteristics listed below.
- Requirements (desired feature, property, or behavior of a system or business) are mapped to the project scope and objectives
- Business requirements are traceable through the project lifecycle. Business Requirements  Business Processes  Business Use Cases  System Use Cases  Technical Designs  Coding  Test Cases  Acceptance by Customer. The project will have a requirements traceability matrix that shows how each project activity maps back to one or more specific business requirement. Refer to work product APP402: Requirements Traceability and Verification Matrix.
- ‘As-is’ business processes are documented and the related organizational and system impacts are understood. A business process describes a series of business actions or operations that together produce a tangible result, usually in support of a function. It manipulates (transforms, controls, or manages) information and/or physical things in business. It is typically described in terms of its inputs, outputs, and/or controls, and can be composed of other processes. It is always described in business terms.
- verify and validate “As-is” manual touch point desk-level procedures
- verify and validate “As-is” business process design flow definitions
- verify and validate “As-is” architecture and interfaces
- known issues with “As-is” business processes are identified and documented
- ‘To-be’ business processes are documented and the related organizational and system impacts are understood. . A business process describes a series of business actions or operations that together produce a tangible result, usually in support of a function. It manipulates (transforms, controls, or manages) information and/or physical things in business. It is typically described in terms of its inputs, outputs, and/or controls, and can be composed of other processes. It is always described in business terms.
- verify and validate “To-be” manual touch point desk-level procedures
- verify and validate “To-be “ business process design flow definitions
- verify and validate “To-be “ architecture and interfaces
- Identified gaps between ‘As-is’ and ‘To-be’ processes are accepted by the client and each gap has a
- manual process work around to address the gap or
- the client has accepted that a system change(s) will be required to address the gap
- The client has approved the ‘To-be’ business processes as the requirements for the system.
- Requirements are clearly articulated and prioritized
- Business & System Use cases have been prepared to articulate how the system will function and the client has accepted these use cases as a foundation for system design.
- Business Use cases trace the sequence of actions performed by a business that yields an observable result value to a particular business actor.  It contains all main and alternate workflows related to producing the “observable result of value”.
  The emphasis of a business use case is on the operation of the business rather than the operation of a computer system.
- System Use cases trace scenarios through the system at the application/component/service level. These show how specific actors interact with the computer system with an emphasis on the operation of the computer system rather than the operation of the business.
- The technical designs reflect the structure or structures of a system that comprise software and hardware components, the externally visible properties of those components, and the relationships among them and are based on the client approved use cases.
- The system logical and physical architecture is complete and agreed to by the client
- The allocation of system requirements to architecture components is complete and agreed to by the client
- The data architecture / model (data flow, data definition, and data migration models) is complete and agreed to by the client
- External and internal logical and physical interfaces are defined and agreed to by the client
- Iteration diagrams showing application / component / service level interactions / interfaces are complete and agreed to by the client
- NFRs and identified and agreed to by the client
- The use cases are leveraged to create test cases and define acceptance criteria.
- test data will sufficiently facilitate the verification of the system acceptance criteria and the system requirements, including the to-be business processes
- Business requirements, business processes, use cases, test cases and acceptance criteria are under project change control.
# Assessment of the Solution Design
The guidance in this section is organized in terms of five assessment steps conducted at various points in time during a project lifecycle:
- Assessment of the viability of satisfying non-functional requirements and constraints
- Assessment of a conceptual-level architecture models
- Assessment of a specification-level architecture models
- Assessment of a physical architecture models
- Assessment of the risk assessment
The steps may be performed in parallel, or in any sequence.
## Assessment of Non-Functional Requirements and Constraints
The goal of this step is to understand if the architecture is based upon a solid foundation of requirements. The reviewer is looking for a current, well-articulated and approved set of non-functional requirements to guide architecture development. A good set of architectural requirements will share the following characteristics:
- They are free from implementation detail
- They focus upon essential elements of the system
- They are consistent with one another
- They are achievable in the context of the “state of the art” budget and schedule
- They are well formed – concise, unambiguous and verifiable
- They are traceable to the business goals
Architecture development depends upon well-formed requirements. A vague statement such as “The system will meet the businesses performance objectives” needs to be decomposed into verifiable statements concerning specific transactions, users groups and targeted response times. The guiding principle is that things must be defined to whatever level of detail is necessary to control the critical aspects of the system.

### Compatibility, Conversion, Migration
If this system replaces an existing system has the architecture accounted for any compatibility, conversion, or migration issues? Some areas of concern include:
- Data from an existing system that must be carried forward (and possibly converted in format) for the new system.
- Existing user interfaces (screen formats, commands, etc) that must be supported in the new system.
- An existing application programming interface (API) that must be maintained.
- Migration from the existing system to the new one that must not disrupt end user service.
- The new system must be capable of operating in parallel with the old system during the migration period.
- There must be a capability to fall back to the old system, if needed, during the first two weeks of operation.
- Old archive data may need to be processes by new system transactions.
- The objective of this question is to identify things that may influence the design of the new system.
### Target Dates
Are any specific target dates specified or implied? The goal is to understand the architecture’s ability to support major project milestones. Areas of concern include:
- Will key architectural decisions be made in time to support the project’s schedule?
- Will standards, reference architecture and models be complete in time to support development teams?
- Will product selections for architecture components be made in time to support the project’s schedule? Is enough time allocated to support acquisition, installation and training needs?
- Can the system’s infrastructure be turned over to the client before the “go live” date?
- Will the client’s operational support of the system be adequate by the “go live” date?
Try to assess the business impact of missing these targets. If any advantage could be gained by improving on the dates, try to assess it.

### Sequence for Implementation
Is a sequence for implementation suggested or implied? Possible alternatives include:
- Geographically – by area
- Functionally – by application
- Organizationally. For example, an office system may be made available to managers first, then to professionals and then to the rest of the organization
- Some combination of the above.

Sequences of implementation concerns the architect should validate are:
- Do purchasing and implementation plans support the sequencing approach?
- Will there be a mixture of new and old technologies that need to be supported for an interim period?
- Are special features needed in the software/hardware to support the implementation approach? For example, if an organizational approach is used, will capabilities be needed to “shut off” solution features until they become generally available?
### Times When Implementation Is Difficult
When will it be difficult to implement a new system? Workload peaks and other factors in the existing systems might prevent implementation at certain times. Will the probability of success be diminished because implementation is scheduled to coincide with:
- Larger processing volumes: weekly, monthly or yearly peaks
- Regular maintenance cycles for hardware or software – impacts both systems availability and staff
- Peak holiday periods
- Planned one-off disruptions due to hardware upgrades or introduction of new systems
- Planned reorganizations
- Facilities changes
### Application Development Environment (ADE) Considerations
Identify issues regarding the project’s ability to support the application development requirements.
- Has the development environment been defined and built?
- Are the developers trained in using the tools?
- Are automated tools available for design, test scripting, regression testing, incident tracking and debugging?
- What type of interfaces and access devices will the system use? Can we support development in these platforms?
- Are special media types required, for example, use of graphics, image, voice or video, in addition to text? Have we accounted for these needs in the tools chosen?
- Are automated tools available for version control?
- Can the development environment support the targeted number of developers in terms of capacity and available licenses?
- How will production and ongoing maintenance activities impact production?
- Will the development system need to be stress-tested for capacity and performance analysis?
- Does the ADE have to support several national languages?
### Development Technology Considerations
Is the project introducing new development technologies that may have implementation, acceptance or “learning curve” issues? Look for specific requirements or givens that will be new or unusual for this client. These might include:
Is this the first time the client or project team will attempt to adopt new development technologies? For example:
- Communication with external organizations such as clients or suppliers
- First use of Internet or object technologies
- First use of cryptography
- First use of development platform (e.g., MVS shop implementing first SP2-based application)
Changes in scale (for example, a large network with centralized processing in a client with only departmental systems installed)
### Development Environment Constraints
Do the requirements specify or limit how the system should be developed and tested? Examine the requirements and current IT infrastructure and standards for any information that will govern how the applications will be developed. For example, determine whether:
- Any application packages have been specified
- Specific programming languages or application generators must be used
- Specific development methods or tools must be used
- The client already has existing application development skills, methods or techniques that you might be able to exploit
- The client has any policies regarding making or buying new system
- The client uses specific testing or certification requirements for proving products or techniques
- The client has a policy, or an inclination, to use third parties for development of their systems.
### Benchmark Requirements?
Will the new system have to be benchmarked? There still may be clients requesting that the capacity of major processing equipment be verified by benchmarks. Others may request performance guarantees.
Benchmarks are very complex, resource consuming activities. Thus, it is important to discuss with the client at this point whether the policy calls for full-volume benchmarks, or whether measurements of sample new applications, followed by modeling or plain projection, might suffice.
It is important to note that these types of benchmarks will most likely be dependent on the newly developed (or acquired) application code, thus making the system design’s completion dependent on the progress of application development.

### Technology Change Management Issues
What will be new about this system for the users? For each category of user, including administration, operators, and end users, identify:
- Are new technologies being introduced that may have training or acceptance issues (e.g., Web Browsers, hand held devices)?
- Does the organization have experience supporting the technologies being introduced?
- Will there be significant skill gaps that need to be addressed?
- Will integration with outsourcing organizations need to be managed?
### Supplier Support Structure
Understand the planned supplier support structure. In most situations, there are some readily identifiable suppliers or third parties supporting the client’s IT systems. The new system might need some elements of support that are not currently provided by them. Identify issues that may be due to:
- Suppliers’ technical skills, strengths and weaknesses
- Engineering manpower and geographic coverage
- Second level support for above
- Commitment to supporting this project from the above groups and executives.
- Support across national boundaries
### Understand Implementation Dependencies
On what will successful implementation of the system depend? Are there any events, systems, people, etc., which constitute dependencies for this system? For example:
- Other systems or facilities that must be implemented or modified before this one
- Availability of key client and supplier personnel
- Availability of new products or services
- Financing being made available
- Key processes not under direct client control.
- The delivery of software in the form of a packaged application solution especially a release with new or bespoke function.
Create a rough-cut critical route analysis of the dependencies upon architecture activities and deliverables.

### Cost Constraints
What cost constraints are placed on this system? Document any explicit cost limits stated in the requirements. Consider especially, costs associated with:
- Development and testing
- System management
- Initial hardware and software
- Running and maintenance
If cost limits have been stated, are they reasonable? From the initial transaction and sizing data, perform a very gross sizing of this system. Perform a rough costing exercise, and compare the result with the expected benefits.

### Expected Benefits
What are the expected benefits for this system? Is there a Return on Investment assumption? It is useful to understand what types and size of benefits the client is expecting from this system. This will provide you a better perspective on the relative importance of certain processes and capabilities, as you make design choices.

### Reasonable Transaction Volumes and Service Requirements?
Does a baseline of volumetric and service level information exist which can be used to develop the architecture? Important volumetric information needed to support architecture development include:
- Transaction rates
- Number of concurrent users
- User and transaction distribution by geographic locations
- Processing peaks
- Service hours
- Out of service allowance
- Response times (best case, worst case, average expectation)
Are the transaction volumes and service requirements reasonable? Can they be supported by the targeted technology? Do you believe that the end users would, or could, generate transactions at the rate specified? As a start, divide the number of transactions per day, or hour, by the number of users and see if it seems reasonable.

### Reasonable Data Volumes?
Are the data volumes reasonable? Can they be held on currently available systems, or, if the requirements lead you to believe a workstation or departmental system will be part of the design, can the data reasonably be held there? Ensure that important data volumetric are being captured to support the architecture development.
- Data volumes to be converted to new system
- Data volume by projected table or subject area
- Growth rates
- Update rates
- Recovery turn around
- Data distribution by geographic location
- Data transmission volumes over network connections
- Archival and retention requirements
### Client Risk Willingness
All requirements have to be weighed with regards to the client’s willingness to accept risks.
- Will the customer tolerate budget, technical or schedule risk to achieve project benefits?
- Is the client culture conservative or decision-making?
- Is the client willing to commit to new technology and products?
### Unusual or Challenging?
What is unusual or challenging about this system? Try to identify characteristics of the system that might make it difficult to implement and therefore will raise the risk that the system will fail to meet its objectives. Use this as a means to summarize the findings for the risk areas examined so far. Examine the following areas for potential problems.
Review Area	Risk Factors
Size and scale	Large numbers (many thousands) of transaction, data volumes or components will be difficult for the targeted technology to support.
New or untried products, services or technologies	Completely new and unproven hardware, software, or techniques, or not used before in this environment.
Unusual application requirements	For example, multimedia or distributed data applications on which the system design and application design both have a high impact. Application designs will be challenging and require expert engineering.
Complexity	Multiple sub-architectures, or many suppliers’ components, or an unusually complex system structure. These will make it more difficult to design and implement.
External interfaces	Interfaces to other systems, including those outside the enterprise that may not exist or may need changes. Also, connections across national boundaries where infrastructure or regulation will impede implementation.
Availability and security	Exceptionally challenging availability or security requirements, such as “the system must never fail.”
Unreasonable Expectations	Client is over optimistic about the benefits to be derived from the technical solution. May be infatuated with technology to the determent of business objectives.
Inexperienced End Users	The public and users who have little or no previous IT experiences. These could be mobile users. Possible acceptance issues which pose risk to implementation and end user satisfaction.
Implementation time scales	Short and inflexible target dates. If, for example, 10,000 users need to be trained in three months, then this represents a challenge to most enterprises.
Development Readiness	New or untried development tools or targeted platforms. Lack of defined development processes. Risk due to instability of development environment, or lack of readiness.
Development Skills	Skills of development team do not match the requirements of the proposed technical solution.
Development challenges	Increased complexity or risk of failure due to the size of the application or the newness of the technology.
Budget Limitations	The system must be delivered at a fixed cost or be subject to cancellation in the event of particular budget conditions.
National Language Support	NLS factors are challenging

### Completeness of Requirements
Assess the completeness of the requirements. Are there major areas of requirements that have not been defined, but should have been by this point in the project? Identify which requirements are missing, and how and when these missing requirements might be obtained. For instance:
- Initiate a subproject to gather them
- Gather them as part of the application development process
- Have a business transformation team (business reengineering) provide them.
- Develop a prototyping to provide them.
Comment upon the stability (are they likely to change) of the requirements. Activities such as a business transformation exercise or a prototyping project are inherently ‘volatile’ because they explore new ways-and-means of doing business and tasks. This means that they may change a requirement (say a set of business processes or the order that they are executed) while the architecture and design effort is proceeding.
All of this apparent uncertainty of requirements is increasingly common in modern system developments. To summarize, consider the following about the requirements:
- Complete?
- Will be complete? (From where will the information come?)
- Stable? (What is likely to change?)
- Are your assumptions reasonable?
- Are they verifiable?
## Assessment of Conceptual-level Architecture Models
### Architecture Context
Verify that the architecture support the client’s and project’s goals and directions:
- Does the client have a strategic IT Architecture that needs to be followed?
- Does the Architecture support the client’s principles and standards?
- Does the Architecture support project goals and contractual requirements (e.g., are performance guarantees stipulated)
- What assumptions were made about the activities, work products and funding of the Architecture group in the contract? Are these reasonable considering the technical problems to be solved?
- How does the project scope define the boundaries of the Architecture?
### Architecture Overview
Review the conceptual architecture as documented in the Architecture overview diagram. Address the following items or questions:
- Are some conceptual nodes going to be more challenging than others are? Which ones and why?
- Order of development and implementation of conceptual nodes?
- Have all connection types been identified?
- At a high level, do we understand the dynamic behavior of the system and inter-node communications?
- Are the major software components identified?
- Have system interfaces, both internal and external been identified?
- Are the user groups and remote locations identified?
- Have the architects prematurely made technology or product decision before understanding the requirements fully?
- Are the major architectural decisions that have to be made been identified?
- Have reusable assets such as Reference Architectures been considered?
- Is there a plan for the project’s architectural activities? Does the plan support:
- The scope of the stated conceptual architecture?
- The architecture decisions that have to be made?
- Work products that have to be produced?
- Any contractual obligations (deliverables, service level attainment)?
### Migration and Integration Issues
Are there any major migration and integration issues with this architecture or design as it now stands?
- From an existing system that it might be replacing?
- From an existing system that it might be enhancing? Take special care when trying to interface network or pervasive computing system components to systems that were never designed to embrace them.
- Does it fit in with existing systems? If no, can these be changed to fit in with it?
- Considerations for data conversion or creation.
- If the system must handle requirements for a Version 1 and a Version 2 of the system, will the system be capable of being migrated from Version 1 to Version 2?
- Access to archive data, especially if protected cryptographically.
Few systems are ever installed into a “green field” so its important to identify other systems or environments affected by the deployment of this system. Ask the question “Is migration to this new system possible and reasonable?”

### System Testing Strategy
Identify how this system will be tested. Complex systems must be tested in parts, and then the parts integrated and the complete system tested.
Show whether the testing of this system will need special attention in later phases. For example, if multiple workstation conceptual nodes are to be installed, you will need to test functions of the workstation, its connections, performance and system management (including software and data distribution). When identifying such tests, bear in mind operational and scheduling constraints and stress testing conceptual nodes.

### Special Design Skill Requirements
Consider especially what special skills are needed to continue the design process. These might be:
- Knowledge of unfamiliar or special hardware or software
- Knowledge of an application package
- Special industry knowledge
- An exceptionally large design team
- A multinational, dispersed, design team
- Network computing skills
- Exceptional security requirements
- Object technology
- System Management expertise
- e-business
### Training for Users and Operators
What type of training or retraining is required for users and operators of this system? At this stage you probably don’t know exactly what the users and operators of the system are going to do. But you may have some strong indications from the requirements what the skill levels of the operators are, for example:
- Bank clerks
- Supermarket checkout operators
- Shop floor workers
- Secretaries
- Graduate engineers.
- Mobile users
- The IT organization
It is useless to expect operators to work the system if they cannot be trained within a reasonable time and at a reasonable cost. If they cannot, the system design is not reasonable and needs to be altered.

### Cost Violations?
Are there likely to be any obvious cost violations from this design? For example:
- User workstation costs far exceed suggested costs per unit in requirements.
- Estimated costs of one host computer exceed cost maximum shown in requirements.
Note: It will not be possible to determine system cost since all the components will not be decided yet. But major exceptions from the assumptions made in the contract should be identified as soon as possible and stated as issues or project change requests.

### Benefits Still Achievable?
Consider whether any of the benefits you identified previously might now be unachievable as a result of any design decisions you have made. If so, document these, and ensure that a strategy is in place to address the issues. Escalate to project management if needed.

### Design Competitiveness
Check that the solution design is competitive. The design may not be the only choice open to the client. There may be other choices offered by groups within the client’s organization, or by external bodies. These may not even be based on a computing solution; they may be business-based such as selling part of the enterprise instead of upgrading its computing systems.

### New and Unusual Characteristics
Assess what might be unusual about this system and its design. Is there anything that would require special attention such as extra project management or risk analysis effort? Considerations include:
- Many new and untried component types
- Many thousands of components
- Many thousands of end-user operators
- International scope, especially NLS and communications considerations
- This system design will cause other connected systems to require a significant change/upgrade
- This system must never fail
- The public at large are its users
- The end users are highly mobile
- Do you know of any other systems similar to this?
- Are there any special safety considerations for the system users or the system components as you can now see them?
### Feasibility
- Is it possible to design, implement, and run this system? Some systems are just too huge or complex to ever work properly. Is this one of those?
- Is undue risk being introduced through the use of unproven technology?
- Do you need to recommend that a prototype of this application be built to ensure that:
- The system flows are possible?
- The system can be programmed?
- The design matches end-user skills and expectations?
- Products work as advertised?
- The system operators can operate the system?
Is the overall complexity of this system so great that those who come into contact with it can never comprehend it? Once again absolute answers are difficult to formulate, but if you suspect the answer to this question is “Yes,” develop a plan of action. Possible mitigation approaches may include:
- Implementing incrementally
- Finding a package
- Removing functionality from scope
- Negotiating reductions in service levels, performance objectives or availability
- Simplifying the design
- Removing the “leading edge” aspects in favor of more proven solutions
## Assessment of Specification-level Architecture Models
### Support Functions
Specify the new support functions identified by the system design.
At this point of the process a number of “application-like” functions have been identified which in reality serve no business function, but rather support the operability of the system. For example:
- Database (DB) design changes and accesses to support mass processing
- Logical DB recovery
- Detection of failure, either at the system or application component level. This latter is especially important in widely distributed applications such as LAN-connected workstation systems.
- Support of mobile users
Common services to multiple applications also should be identified:
- Operating functions such as start up and shut down
- Single logon to all applications
- Backup, archiving and restore of data
- Data staging services to import / export data:
Event control and work flow of business processes
- Mandatory flow control
- Asynchronous events handling
- Application level exception processing:
Monitor functions
- Logical error handling
- Persistence
- Hooks to monitor availability and performance
At this point you should verify that sufficient information has been collected at the functional specification level in order to:
1. Proceed with the detailed design regarding the use of these facilities
2. Ensure that these features are incorporated in the component model
3. Pass the specifications to Application Developers for inclusion into the development process
In arriving at the present architecture models and application models several assumptions may have been made regarding the feasibility of certain software facilities and interactions. Some of these facilities and interactions will be provided by system control software but others may have to be provided by application programming. For example:
- Application cannot forward messages so it has to perform stand-in processing
- Application can tolerate parts of a DB being “corrupt”
- Check with the Application Development process team (program designers) that these functions can be provided.
### Prototype
If the system, or part of it, looks particularly challenging, especially regarding end user operation and acceptance, it may be necessary to build a “proof of concept” prototype. Proof of concept prototypes is also a good practice to test and validate any unknowns about the design and/or development environment. For example, a proof of concept prototype could be used to confirm / test that a message queuing between a workstation and the central host will work, give the required performance, and maintain integrity when the cable is pulled.
Remember that if your application development (AD) environment is new, you may wish to prototype it. For example, you may wish to set it up and try developing a small application, as proof-of-concept that the components of the AD environment will actually fit together and perform at the required level. Be aware that prototypes need to be carefully controlled and thought out. If not, they can soon consume enormous amounts of resource. It is important to remember that a prototype is testing particular aspects of the system solution, and that it may be missing other features necessary for the system to meet client expectations. Thus, avoid the danger of letting a prototype become the real system to satisfy schedule constraints and end user demands. Realize also that the prototype should be evaluated and how much effort it will take to do the prototyping.
### Development Resources
Define the development resources required for the infrastructure of each node, for connections between functions, and for testing.
Note that the development environment may already have been defined. If so, determine if any of the newly defined system function creates additional requirements. Add more detail on:
- Specific hardware functions to be supported
- Data management/creation
- Connections required for testing
- Specific compilers/tools required
- Number of developers required.
### Implementation Dependencies
On what will successful implementation of the system depend? Reconsider what has changed appeared or disappeared.

### Significant Changes?
Assess the impact of these changes on the schedule for implementation of the system, rejecting any alternatives that cannot be implemented within the schedule. For example,
- The first use of network or pervasive computing
- The first use of PWS
- The first use of mobile technologies or the Internet
- Distributed systems
- Changes of scale, such as increasing the numbers of users from hundreds to thousands
- Providing a service to users outside the organization for the first time
- Providing service to users/businesses in other countries.
Remember that real people have to use this system. If your design is a radical change for the people or for the organization, they simply might not be able to absorb the rate of change, and the system would not be used as intended, or deliver the expected benefits.

### Major Cost Headings
Summarize the major cost headings. As the cost model coalesces, is it still in line with proposal assumptions? Start to fill in the major items under headings including:
Initial implementation
- Hardware
- Software such as packages
- Physical installation
- Development and system test
- Development of system management functions
- Acceptance test/pilot running
- Mass implementation
Ongoing operation
- Operating and support staff
- System maintenance – application maintenance staff and facilities
- Hardware and software maintenance
- Communications
- Software licenses
- Environmental costs
Expansion and growth
- Hardware
- Software rework/amendment
Although the data may not be fully available its useful to build a framework that can be completed in the later phases. Raise issues where cost assumptions may be exceeded (see item below).

### Within the Budget?
Is the system still within the budget? Has the workload increased or are the component and operational models defined significantly complex to the point where the planned budget will not be large enough for typical product solutions? For example, if the budget is based on an average cost of 5,000 dollars per user, can the function be provided in user workstations (and/or host systems) that cost no more than 5,000 dollars per user? Bear in mind that there may be trade-off between capital equipment costs and development or operating costs that also need to be taken into account.

### Benefits Still Achievable?
Are the benefits still achievable? Do not spend long on this question, but consider whether any of the benefits previously reviewed might now be unachievable as a result of any design decisions made. If so, document these, and ensure that the sponsor understands it.

### Acceptability of System
Is the shape of the system acceptable to the client? Has it changed to the point where it no longer matches what the client wishes to buy? Will they think it is too large and complex for the applications or services they want to run? Will the system sponsor be able to “sell” the system to the intended users? Can the service levels for the end users be met? Given the revised data and function placement strategy and infrastructure support functions, can the service levels that the users require of the business processes be met?

### Reasonable Design?
Check this system design for reasonableness. Examples of why this system might not be reasonable could include:
- Too complex
- Too advanced
- Too costly
- Unmanageable
- Unprogrammable
- Unsupportable
- Needs technology that is not available or could not be developed
- Too challenging a time scale for implementation.
### Character of the System
Review the character of the system. Check that the targeted infrastructures still comply with the architecture:
- Has their character changed significantly?
- Can the processing centers handle new workload?
- Are new infrastructure components sufficiently sized?
- Are the LANs and WANs defined in the system architecture well matched to the traffic they have to carry?
If necessary identify the reasons why the system design and the architecture do not match. Have the requirements really changed as the design was developed, or did the design not pay enough attention to the architecture? Plan whether the architecture is to be changed or the system design is to be reworked.
Will any of these issues affect the availability of the new system? For example, if the new system is to run on an existing processor, operating system image, or network configuration, are the availability characteristics of the existing platform consistent with the requirements of the new system? Include environmental maintenance and physical constraints such as ATM or printer hopper capacities in this evaluation.
## Assessment of Physical Architecture Models
### Verify Disaster Recovery Design
Verify the components of the disaster recovery and associated nodes and connections. Consider the components of the disaster recovery node(s) and also any support components in the node(s) being protected by the disaster recovery node(s). The disaster recovery site has to be kept in step with the normal business system, if it is to be able to take over the processing in the event of a disaster. The requirements should have told you how up-to-date the disaster recovery site must be. Perhaps it is sufficient to take backup tapes over to the disaster recovery site at regular intervals. However, some designs may require more recent data. Perhaps there is a need for functions to “collect” any changes to key data records or files, and then transmit these changes via some “sender” function, to a “catcher” function in the disaster recovery site. Check the design for:
- The existence of collector, sender, and catcher software components
- Adequate processing and storage capacity at the disaster recovery node (note that the disaster recovery node may have its own regular workload)
- The existence of satisfactory connections
- The means for the switch-over of the network (if required)
### New Support Functions?
Review the list of new support functions, and check whether there have been any changes, additions or deletions.
Identify which functions cannot be provided by the components selected (i.e. no reasonable match is available on the market). Then decide whether:
- You have to return to the use case model, analysis models or design models to reassess the need for the specific facility. It is likely that by slightly changing the design or easing up on the requirements the need for this facility disappears.
- You have halt the system design process and request a review with the executive sponsor.
### Additional Development Facilities?
Define any additional development facilities:
- What new tools will be used to develop and test the new system?
- What new skills will be needed?
- How will these be acquired – retraining existing staff or hiring new?
- How long will it take to create the development environment?
- How much of the development environment will need to be retained for ongoing system maintenance?
- Have the development functions been assigned to nodes? Included in the sizing data?
- Have the connections between the development and production environments been defined in the system specification?
### Skills and Training
Identify the skills and training that will be required for end users, operators, and support staff.
Now that specific components with which the system will be implemented have been determined, update the training assessment that was created previously, and identify any new skills that will be required on the part of end users, operators, and support staff. Based on this, identify the specific training that will be required for each group (end users, operators, support staff) and potential sources of that training (in-house education staff, vendor-provided training, etc). Do not forget any National Language Support considerations. Determine if benchmarking of parts of this infrastructure is necessary. Some clients might call these proving or certification trials. Benchmarks may have been called for by the client’s acceptance process. A benchmark may also be needed if mapping the largest node’s workload onto the selected components created a borderline capacity projection. On the other hand, even if the client’s acceptance process normally calls for a benchmark, the projected loading level for the selected components may be sufficiently low to convince the client that a benchmark is not actually needed.
If a benchmark is needed, that recommendation should be made now, in order to allow time for preparations and to guide activity in the Infrastructure Components phase.

### Identify Possible Product Sources
Identify possible sources for the products selected including client- and vendor-developed products. Do suppliers and products have to support certain criteria and standards? What is more important to success, use of emerging technologies for optimum solutions or proven concepts? Vendor selection should be based on two criteria:
- Technical aspects.
- Non-technical aspects such as presence and support in the country, market acceptance, and the likelihood they will be around in the future.
Remember that some clients might prefer the purchasing department to make the final choice of supplier for certain types of component.
### Refine Cost Figures
Refine the costing. Check whether the system design already has exceeded its budget. Check whether the design is still competitive. For a system with few different types of nodes, a quite accurate estimate can be made. For a system with many nodes of different sizes, accurate costing will be possible only after the design is complete.
Add more detailed headings to the cost summary you started earlier. Remember to consider:
- Maintenance
- Development
- Operations
- Communications facilities
- Personnel
- Space, power, and other facilities
- Supplies
- Education.
### Additional Product Benefits
Review the selected components for additional potential benefits to the client beyond those they explicitly stated in the requirements. Plan how they are to be treated in evaluating the alternative designs. Can the benefits be added to the system evaluation criteria? Can the benefits be used to assist the sponsor in selling the system to others in the client organization?
### Benefits Still Achievable?
Are the benefits still achievable? Do not spend long on this question, but consider whether any of the benefits you previously reviewed might now be unachievable as a result of any design decisions that have been made. If so, document and ensure that the sponsor understands it.
### Ability to Deliver
Review the system for reasonableness:
- Does the complexity of the system match the type of function it is designed to provide?
- Does it match the skill and experience of its users? Of its operators?
- Does it have too many (or non-complementary) architectures?
- Does it have too many component types?
- How effective is system-wide security? Do all the security components work together to provide protection?
- Will the system meet its availability targets?
- How many components have to be operational for the users to receive service?
- How many staff will be involved in recovery from a failure?
- How long will recovery take?
- Are there enough components to ensure recovery?
Do the products and techniques on which the system is based match its expected life? An interim (tactical) system with a short life can safely be built using old technology because it will soon be discarded. A system with a long life expectancy (most systems) should be built on up-to-date technology and methods so it can be maintained and expanded to support future requirements.
## Assessment of Technical Risk
### Risk Identification
Start by hypothesizes on the possible risks using the results from the assessment steps. Test the hypothesis. Find potential disconnects among the work products or within the architecture models. For example, a disconnect would be a use case that is not reflected in the analysis model or an improper design model. Once the disconnect is identified determine if it is the source of a risk or evidence of another hidden problem. List the technical risks in the categories:
- High – will stop the project completely (critical)
- Medium – might stop the project completely (potentially critical)
- Low – a problem but not a critical one (nuisance)
By identifying a risk in any of the above categories you are signaling that you consider there is a reasonable probability that the events that define the RISK might actually happen. You need to decide what ‘reasonable’ actually means in your context. Is it 10%, 30%, 50+%? You will need to take a consistent view so that you don’t cause confusion.
Look deeper into your identified risks as to how they might make the project and therefore the successful delivery or running of your system, fail.
- It will not work at all
- It will work with limited function, service, or benefits
- It will work but will be delivered late
- It will work but will cost too much to develop (often associated with late delivery as above), or operate
- Some of the above may be acceptable and not represent a risk.
Identify the high and critical risks and decide upon containment actions for them. This is an especially appropriate action for a system design team to do. If the requirements are too difficult to understand do not proceed with the design but do more work to clarify them. In particular identify those risks that need urgent action. A risk may be graded as medium, but the need to deal with it may be much more urgent than a particular high risk that will not stop the project for say a year.
- Ensure that your issues list is updated with your new risk assessments, containment’s, and urgency.
- Communicate your risks and your plans.
- Make sure your risks and their associated containment actions are communicated, where appropriate, to the next phase of the design for that phase to work with them. If you do not have a risk containment plan for each risk seek assistance.
### Interview Guides
The following guides provide key questions to assist in identifying risks.
Requirements
Interview Questions
Is there an official requirement statement and who approves it?
What is the relationship between AD and users?
How are defined requirements verified in the design phase?
What is the process to ensure a design element satisfies the requirement?

Technical Stability
Interview Questions
What technology do you have installed today?
When a failed component has to be replaced, does it require the complete network technology to be put out of commission?
Can you identify other projects that have successfully used similar technologies in the way defined by the component and operational models?
Are the interfaces described in the system context diagram using proven technologies?
Is there a requirement for data synchronization? If yes, are there production references of a similar implementation?

Technical Complexity
Interview Questions
What types of application transactions are you running? (For example, functions shipping, remote procedure call, transaction routing, terminal applications)
In your transaction manager environment, is load balancing required?
In your transaction manager environment, what interface attachments are required? (For example, DB2, IMS, MQ Series)
What is the request flow for applications in this environment? (For example, peer-to-peer, distributed, broadcast?)
Is complex routing required?
Are there specific features required for this facility? (For example, guaranteed delivery, persistent data, time-outs, priorities)
If messaging is used, what is the maximum message length for your application?
If messaging is used, what is the maximum number of messages that can be stored on the queue at the same time (maximum queue depth)?
What object management framework is your using? (For example, COBRA, DCOM)
What languages does your ORB (Object Request Broker) need to support? (For example, Java, C++, Smalltalk, etc.)
What is your philosophy for handling a mixed workload? (For example, each application on its own server, multiple applications on a bigger server)
What languages need to be supported in the future? Does the layer of business objects need to provide guaranteed responses?
Does the client have experience in implementing or supporting the technologies prescribed by the architecture? If no, how is that being addressed?

Technical Integrity
Interview Questions
What is your maintenance window for the system, application, database, and network?
Do you need to support multiple concurrent users?
Do you need all components continuously available?
Is there a single point of failure in any component?
How would a power outage affect your availability?
How do planned changes affect availability?
Are there single threaded areas that would impact concurrent users?
Can the components of your systems exploit SMP or cluster technology?
How would a breach in security affect availability?
Are there severity-based response time criteria for your vendor support?
Can this component take advantage of redundancy to improve its availability?
What are the performance objectives for this component?
How can you verify that this component is meeting its performance objectives?
Is there a threshold of performance degradation that would trigger changes to this system?
Is performance to be measured at the source or at the destination?
How is the load to be generated for performance testing?
Do you have any response time objective in your Service Level Agreements?
What is your expected average and peak transaction rate?
What is your average and peak utilization?
What tools do you use for performance monitoring, reporting and tuning?
How do you handle workload balancing across multiple servers?
How do you control the resources (for example, CPU, storage, DASD) used by individual users?
How is response time measured (for example, end-to-end or by individual component)?
Can your transaction be backed out if any failure occurs before its completion?
Do you require two-phase commit?
What kind of serialization and locking mechanism are you using for database and distribution service components?
Does each interface in the process validate its input?
Does this component have built-in integrity checking?
Does each major step perform logging?
Do you require time synchronization?
Are there any time dependencies in this component?
What is the granularity of backup and recovery?
How long is your backup window?
How long is your recovery window?
Can backup take place while the component is in use?
Do you have any requirements for roll forward recovery, in this component?
Do you have any requirements for point-in-time recovery?
Is this component responsible for its own recovery, or does it rely on an underlying component?
How do you authenticate a user?
What controls exist to prevent unauthorized access?
What level of authentication is controlled?
What level of access control granularity do you require?
Is third party authentication required?
Is an audit trail required?
What level of regulated security is required?
What level of access control granularity do you require?
Do any of your systems transmit user Ids and passwords in the clear across the network?
Are there any hard coded passwords in this component?
Is your security server centralized or distributed?
What is the users’ expectation of the availability, in hours, of this application?
How would this project affect the capacity of the client workstations?
How quickly do you need to respond to unexpected growth by changing capacity?
How quickly can you reallocate resources to handle unexpected workload?
What is your rule of thumb on when to seek increased capacity?
How should this system react when you reach capacity?
Do you have a help desk? If yes, do they support this component?
Do you have a centralized focal point for control of this component?
How are problems reported and managed for this component?
Is there a problem determination procedure for this component?
What is your change control process?
Are there automated alert processing and notification functions within your components?
How do you distribute SW updates?
Are there any requirements to support multiple languages?
Have you had a security audit recently? If yes, what were the findings and how were they acted on?
Have you completed a process to remove unused or dormant Ids?
Are there reports for identifying repeated unauthorized access attempts? If so, are they followed up
Is there a limit on the number of systems that can share the password database?
What happens when the communication between the remote site is temporarily lost? How quickly would your security solution resynchronize the separate password databases?
Does this component offer translation between two different security mechanisms?
Can this security solution fully recover from a complete loss (corruption) of its primary password database? How long would it take, and has it been tested?
Is there a documented process for creating new user ID’s and groups? Who administrates it?
Is there a documented standard for your group structure?
Do you require data replication? If so, how current do you require the replicated data to be?
If there is a disk failure, can the database continue to operate?
If the database runs in a cluster, how will the loss of a node impact the database availability?
Can your database, tables, index be supported across multiple volumes?
What is the maximum table size and database size for your application?
What are the transaction types in your application? (For example, adhoc or pre-planned, simple or complex queries, OLTP update)
Are there specific features required for this database? (For example, store procedure.)
Does your database take advantage of the unique features of your host? (For example, workload manager, etc.)

Architectural Qualities
Interview Questions
What is the maximum number of active users?
What is the maximum number of connected users?
What is the maximum number of defined users?
What growth rate do you anticipate?
How much transactional data is involved?
How much repository data is involved?
What is your philosophy for managing your increase in capacity? (For example, larger systems or more systems)
What does your client consider when identifying a cost-effective solution (such as the cost of software, hardware, availability, maintenance, scalability, manageability, services, and skills against the number of users)?

Ability to Deliver
Interview Questions
What is the team’s experience in using the technologies prescribed by the architecture?
What skills do you currently have in this component area (e.g., Java, MQSeries, CORBA, CICS, etc?
What skills can you purchase for this component?
What education and training is available in this component area?
What skills are missing for this project?

Development Approach
Interview Questions
What AD Methodology are you employing?
Do you have documented application development methodology, guidelines, procedures, and/or standards manuals?
What are the development phases of the your AD process?
If it a full life cycle methodology (i.e., planning through production support and maintenance)?
Where is the greatest and least involvement of the business user in the process (i.e., requirements, design, testing, etc.)?
What is the perceived business merit of the current methodology?
Why are you not currently using a methodology?
What is the methodology basis (structured, IE, data/process, OO)?
What automated tools do you use for AD?
How are rapid delivery, incremental development, and prototyping handled by the methodology?
Does your methodology provide client server support or support for distributed applications?
Is there a process owner for the software process?
Who enforces standards and procedures?
Who does analysis?
Are design and code reviews coverage measured and recorded?
Is there a formal management process for determining if the prototyping of software functions is an appropriate part of the design process?
Is a mechanism used for ensuring traceability between the software top-level and detailed design?
Are internal software design reviews conducted?
Is a mechanism used for ensuring traceability between the software-detailed design and the code?
Are coding standards applied to the development project?
Are software code reviews conducted?
Is a mechanism used for configuration management of the software tools used in the development process?
Describe the checkout and check-in for source code?
Are the development environment defined and all components installed and operating?
How do you manage testing within each component?
Does your test environment represent your production system? (For example, software release level, hardware, workload)
Can processes associated with this component be automated? (For example, backup, log switch)
How do you manage performance tuning within each component? (For example, hardware and software,
What naming standards exist in all component areas?
What are your existing standards?

# Assessment of Cutover to Production
The objective of this section is to identify steps and to corroborate assumptions and logistics identified in the Implementation Cutover to Production. The questions are intended to supplement those found in the Viability Assessment work product description. This section may be considered a quality control checklist for consideration during the period leading up to full deployment.
Deployment, or cutover planning, is a set of tasks that both the client and project team agree are necessary to install and test the new system. Verifying that the cutover plan is achievable and complete is crucial to ensuring the plan is built properly, that the installation will be seamless, and ultimately, that the user will not be unduly interrupted.
Testing a cutover plan encompasses the following major areas:
- Ensuring that data conversion and data migration can be implemented securely
- Verifying the readiness of all hardware, software and infrastructure components
- Verifying that user needs before, during and following cutover, will be met
The steps may involve large communities within the organization, from purchasing to facilities management, and/or from training departments to help desks. These verification steps must be coordinated with the joint teams involving the project manager (IBM and client), systems architect, developers, testers and business users.
When verifying cutover plans, some high-level recommendations include:
- Adhere to a regimen of staged sign-offs or approvals (e.g. “go” / “no go” decisions) as you execute the cutover plan to ensure that tasks within each step do not get missed
- When qualifying what functions require scrutiny in the cutover plan, consider those functions which match the criteria “high risk, high usage, and /or high visibility”
- Ensure all contractual obligations will be met by the implementation
- Validate that all objectives are met as evidenced through system testing

The following is a checklist of verification steps form the basis of testing an Implementation Cutover Plan:
1. Verification of training, education, and skill levels
2. Verification of timing of cutover including schedules and milestones
3. Verification that infrastructure and components are in place
4. Verification of site surveys, site plans, and specifications
5. Confirmation of user support readiness prior to, during and following cutover
6. Confirmation of hardware and software acquisition, delivery and installation logistics
7. Verification of data backup, conversion and migration procedure
8. Review Preparedness and confirm expectations of user community
The following subsections describe these verification steps in more detail:
## Verification of training, education, and skill levels
Selected training strategies are consistent or compatible with the current or planned end user technology environment
- If several methods were used to provide training, verify the suitability of the training method to suit user needs
- Where a group of users have difficulty completing work in a test environment, re-evaluate whether the training method or level of detailed instruction is at fault
- Additional training is planned to provide expanded user knowledge and in-depth training for key users
- Procedure manuals and user instructions have been exercised during Acceptance testing. Errors caught during testing should be re-tested using walkthroughs and pilot install techniques
- New roles staffed and new responsibilities are documented as verified during User Acceptance
Consideration has been made for those who will be involved in pilot tests (advanced training) or parallel testing (additional staff) when staffing
Objectives of user training have been met as measured by the user community
All usability and operability functions are accepted by the user community
Customization of menus required to access new system has been completed and verified
Typically, main menu panels must be updated to enable access to new system functions
- All user ids, passwords, and network access have been made available to meet the rollout schedule
- Maintenance team to support new application is staffed and trained
- Mentoring has been considered as a means to augment training
Responsibility has been assigned and individual acceptance of the role has been obtained
- A pre-rollout pilot is scheduled to verify user training, user documentation, and staffing requirements
- Cutover rehearsals have been scheduled and conducted
- Use the experience to refine time estimates, document procedures, and identify gaps
- After making changes, walk through the schedules and documentation to ensure that the process continues to ‘make sense’
## Verification of timing of cutover including schedules and milestones
- Verify that schedule does not conflict with highly ‘sensitive’ timeframes such as period end, month end, quarter end, etc. Also, avoid periods of high business/transaction volumes, if possible
- Sequencing of activities has been reviewed
- Schedule allows for reasonable delays in shipping or setup such that equipment can be operational before the cutover or pilot processing begins
- Schedule allows time for restoration of the old system (fall-back plan) prior to the final “go/no go” decision. Include:
- Library reallocation
- Disk/file reallocation
- Existing database and file conversion
- New database and file loading
- Network switch over
- System parameter switches
- Old system backup
- Cutover plan is built according to milestones (e.g. cutover tasks to be completed 2 weeks prior to going live, 1 day before going live, weekend of going live, first day after going live, etc.)
- Time is allowed after cutover before clean-up operations commence to ensure system stability
- Skills have been identified:
- Proper resources have been assigned/committed according to the schedule
- Each task is assigned to an individual and confirmation of the completed task will be relayed to the cutover coordinator
- A clear and complete responsibility matrix is agreed upon and communicated to each team member, including users, quality assurance (QA), technical support, architects, network specialists, and project managers (PMs)
- Note that although frequently the test manager and application development manager are not directly involved in the cutover, they should be on site during the cutover for support purposes because of their experience with the system
## Verification that infrastructure and components are in place
- Project reporting procedures, escalation procedures, and issue management are in place up to the client management and sponsor level until the project is officially closed
- Change Management is engaged and prepared
- Problem Management is engaged and prepared
The Project Manager should be prepared for “hard-ball” decisions on whether a problem is really a Severity 1, 2, or 3. Although it may contradict the original plan, with the stakeholder’s approval, many installations often decide to proceed into production with Severity 2 problems outstanding depending on the risk incurred
- Space allocation is checked against latest volume predictions
- Operations and systems management teams are fully advised and have approved desired schedules including staging of systems, and backups, as well as fallback/recovery stages
- A centralized ‘burn-in’ center has been established to setup workstations, load software and verify consistency and accuracy of installation prior to shipment to the final destination
- This is an effective tool to maximize use of resources and improve quality of the workstation configuration
- The burn-in center has an additional advantage of providing a single receiving point for components (e.g. UPS, PC, cables and software may come from different locations)
Installability testing performed:
- Is the installation document complete and correct?
- Is machine-readable data in the correct format?
- Can the JCL or EXECs be tailored to meet local standards
- Are all required components in the installation package?
- Does the installation package include test data? Does it run?
Are installation tuning parameters provided? Are they documented?
Environment testing performed:
- All required members and files have been transferred to the production libraries
- Application works in production environment (e.g. through a pilot test or running the application on the weekend etc.)
- All batch jobs run with all job and file dependencies satisfied and can be completed within batch processing window
- All situations, such as daily and month-end, tested
Metrics are in place for measurement and processes developed to correct deficiencies
- Processes in place to collect / assimilate all information
- Performance measurement tools enabled
- Predicted volumes in place, reporting scheduled and reporting audience prepared
- Security procedures have been tested during Acceptance testing and all issues resolved
- Old system has been left in place for backup purposes for an adequate period of time although transition to the production environment has already occurred
- Software Configuration Management (SCM) is established:
- Service level objectives are in place
- SCM activities are planned, and the plan is documented and approved by all stakeholders
- Selected software work products are identified, controlled and available
- Changes to identified software work products are controlled and problems are recorded/reviewed
- Installation includes a basic installation verification check to ensure all components are operational
- Affected groups and individuals are informed of the status and content of software baselines
- Project follows a written organizational policy for implementing SCM
- A board having authority for managing the project’s software baselines exists
- A group responsible for coordinating and implementing SCM for the project exists
- Members of the SCM group are trained in procedures and methods to perform SCM activities
- Standard reports on SCM activities are developed and made available to affected groups
## Verification of site surveys, site plans, and specifications
- Inventory of locations including current addresses, cable identification, and LAN ids is available
- Updated inventory including cross-reference of changes to current sites and new locations is available
- Transition plan to accommodate changes is established
- All outstanding orders are checked:
- No backorders exist
- All deliveries are scheduled
- All receiving location addresses are verified and personnel have been notified
- All shippers are confirmed
- Access to all locations by assigned personnel is authorized, including third party suppliers, and their agents
- All phone orders, lines, number assignments, deactivations, and reconfigurations are confirmed
Circuit diagrams are updated and complete
## Confirmation of user support readiness prior to, during and following cutover
- Support roles are defined and staffed
- Support criteria are defined:
- Help desk questions
- Error reporting processes
- Feedback mechanisms
User support criteria is met as verified during acceptance tests
- Requirements compared to final delivery functions are traced, a gap analysis has been performed, and final sign-off from users has been obtained
- Full staff support is in place during cutover, key processing periods (first business day, weekend, month-end, etc), system catch-up phase (recovering from deferred transactions during planned system outage), and back-out/recovery, if necessary
- Communications plan is established: Cutover to a new system utilizes more staff and impacts more people than at any other time in the life of the project. Although communication occurs throughout cutover, the importance of effectively communicating – progress, problems, updates – is critical to successful deployment. A cutover ‘kick-off’ meeting is one technique that sets the direction for all follow-on tasks. The cutover kick-off meeting should have, as its purpose, to review all items which are new and potentially unfamiliar to the participants such as:
- Objectives of the rollout and the rollout acceptance (exit) criteria
- Roles and responsibilities of each participant
- Cutover plan and schedule and fallback procedure in case of an outage or failure of the new system
- Batch data transmission schedules
- Contents of the documentation
- Help desk procedures
- System support procedures
- Production procedures
- System startup and shutdown procedures and schedule
- Security procedures
- Data backup and restore procedures
- New report formats and distribution schedules
- Manual procedures which are being introduced
- Audit procedures
- Processes to be followed to phase out the old system
- Executive communications very important – A status call-in phone number is established for executives/decision makers to hear a voice recording of up to minute progress during cutover. In practice, this has proven to be a very efficient, effective, and time/cost saving technique to keep executives informed
- Notification process is prepared and ready to send according to defined schedule identifying each planned disruption
- A communication plan must also consider what information is pertinent to the general public, especially in the light that the new deployment may suffer setbacks in terms of decreased functionality, decreased performance or total rollback to conditions prior to cutover acceptance. This part of the plan and its various contingencies must be developed and reviewed very early in the cutover strategy process to enable all stakeholders to consider wording, timing, media, etc.
- Pagers are available to contact decision-makers during cutover
All workflow procedures and processes are consistent with the ‘new’ system and infrastructure. (Cutover will undoubtedly be ineffective if the business process surrounding the new system implementation has not been effectively tailored.)
## Confirmation of hardware and software acquisition, delivery and installation logistics
- Hardware / software meets scalability targets for deployment based on expected transaction volumes and rollout targets
- Risk mitigation process is in place in case volumes exceeded and/or schedules advanced
- PC software and associated device configuration standards are established, and rollout and installation plans are verified via a walk-through
- As cutover begins, there will a need to identify, and correct misinformation. Here are some of the situations which often occur and the plan must address them:
- The client machine is not the same configuration (software or hardware) as that originally inventoried
- The client machine is correctly configured but when software is installed, it appears to operate differently than expected (e.g. Perhaps due to additional conflicting software, or a virus)
- The client machine is correctly configured and the installation goes smoothly, but the user operates the device in a non-conventional manner. This concept of users of new systems acting in an erratic manner is frequently prevalent and may cause large increases in Help Desk calls, or server transaction volumes.
## Data backup, conversion and migration procedure verification
Backup procedures are in place and scheduled
- Application must be capable of being restarted after failure (e.g. restoring data sets, backing out changes, restarting or canceling jobs
- Copies of critical programs, data, and documents stored off site as part of the vital records program
- The following should be tested:
- Can a checkpointed program be successfully restarted from a checkpoint?
- Can a batch job be successfully restarted at any step marked restartable
- Can a batch job be successfully cancelled and rerun another day
- If an on-line program fails, are partial data updates correctly backed out?
- Can vital record data be used to recreate the application?
- All tasks that must be performed manually are staffed, backups are assigned, backout procedures are in place, and training has been completed
- Conversion, migration, and archive strategy and criteria are in place
- Procedure to access archived data is documented and distributed to all users and has been tested
- Data conversion specifications may be site specific; thus, instructions for each site have been tailored as necessary
- Data owners (3rd party, department, individual) have signed off acceptability
- Data verification reports have been run and checked for accuracy (hash totals)
- Data initialization verification has been performed
Run jobs with null data as typical with conditions to be expected of a new system (e.g. new period end, new month-end, etc.)
All entry and exit criteria are met during User Acceptance testing under ‘live’ conditions
- Each data extraction, conversion, data formatter, copy or archive process is exercised, results are verified under ‘live’ conditions
- Data conversion/ migration should be tested immediately before going live and data used as input to start-up cycle to test compatibility with new system being implemented
Define and communicate limitations of Database Fallback and Roll Forward
After x number of production hours/days, a database fallback may no longer be possible and/or practical. The window to update the old database with production transactions since the cutover may be impractical or impossible
Test and verify all interfaces to the new system including manual, automated
All systems have interfaces, whether to a human/manual process, a legacy system, or a recently introduced client server application. Frequently, interfaces involve business partners such as EDI applications, web applications or electronic transmission of business data. Each of these interfaces represent points of failure which must be thoroughly tested, results verified and signed off before deployment.
## Review Preparedness and confirm expectations of user community
- Degree of schedule attainment during Acceptance testing is an indicator of level of user readiness
- Think about the unthinkable – develop a fallback plan and establish a formal plan to invoke it with the user community. The plan must include go-no go decision points, communications steps, in addition to full details. Be clear in terms of the desired fallback position (eg. How much to back out, final configuration/ level of software the client machine should end up with, etc)
- Make precise decision trees with user executives about who calls a fallback
- Do not assume that users will continue to react the same way immediately after cutover
- For example, users who were used to getting system responses in a certain time period, knowing there was a new system at work, would do things that were not at all reasonable such as re-booting, canceling and re-entering etc. This drives the transaction load up on parts of the system far beyond the design points
- As an offset against getting unexpected behavior from users, test their role in cutover by reviewing expectations with them. Provide users with an understanding of the following considerations:
- Value and Function they will obtain right away
- Value and Function they will see over a longer term
- Limitations or impact they may expect in the short term, such as events that may cause them to feel anxiety in the first 5 minutes, during the first week, etc. Rehearse the steps to communicate problems so that implementors can fix them
- Based on the pilot or user acceptance tests, review changes that have occurred that they may not be expecting
- Rehearse the users role in the fallback plan
- Try to predict the number of Severity 1, 2, and 3 errors that exist before cutover starts and those that will arise during and following cutover. Attempt to get user agreement to this number
- When users know they had approved a cutover with X number of Severity 2 errors, this can make the hours/days/weeks/ after cutover much less stressful
## General Hints, Tips, and Considerations
- The process of thinking, planning and conducting rehearsal cutovers and fallback provides the team with a great deal of confidence in the final cutover. Cutover rehearsals are done with a view that you will never need to fallback. However, the process of thinking about fallback often points out areas where partial fallback is possible. This in turn provides insights to cutover activities that can be reorganized to make the staging of the cutover in smaller phases with intermediate checkpoints a possibility (e.g. some place where data stands still for a little while). This can reduce project risk
- Perform a risk assessment
- The cutover plan must be very thorough. Consider using static walkthroughs. Review what to test. Review schedule and resource plans. Ensure that any vacation constraints are reflected in the project plan
- Focus on high risk, high usage and high visibility functionality and/or applications. (Note: sometimes only one application is being implemented and a focus is on the functionality)
- Set client expectations at the outset
- Ensure that you have client consensus/sign-off
Document for each step of conversion process:
- What the major points of failure or risk are
- Completion criteria
- Steps to backout
- Steps for manual override
Encourage a “Learning Organization” – hold a post-implementation review for “lessons learned”
## Typical Roles and Responsibilities
Systems administration
- Operations Test Exit Criteria passed
- New Operational Procedures developed
- Implementation steps and tasks defined, documented and understood
- Education and/or training completed prior to implementation for key staff
- Security authorization requirements defined, documented and understood
- Monitor system to validate new capacity plan meets SLA (Service Level Agreement) targets (e.g. users, CPU capacity, channel activity etc.)
Database management
- Tools identified for implementation and cutover
- Data migration plan documented (and reversible)
- Data conversion plan documented
- Plan for data maintenance during data conversion timeframe from source production database
- Define, document and communicate limitations to database fallback and roll forward timeframes
- Familiarity with new database architecture
User Help Desk
- Included in operations high level training
- All key contacts should be documented and/or an escalation procedure well defined during early production stages
Network/LAN/WAN Support group
- Included in operations high level training
- Operations network test exit criteria passed
- New network operations procedures developed
- Implementation steps and tasks defined, documented and understood
- Education and/or training completed prior to implementation for key staff
- Security authorization requirements defined, documented and understood
- Monitor network to validate new capacity plan meets SLA (Service Level Agreements) targets (e.g. transmission time, block sizes etc.)
- External client validation of connectivity to new functionality/application etc.
HVAC systems engineering
- Air cooling capacity planned and verified, and monitor for production use
- Installations coordinated and/or completed before cutoff plan implemented
- Update Business Continuity Plan if applicable
- When implementation exit criteria has been completed, plan to remove old hardware configuration should be executed
Project manager
- Creation of Go-Live report
- Act as cutover coordinator or oversee those to whom assignment was delegated
- Client sign off on all deployment criteria
- Part of team to develop final recommendation to executive sponsor
# Assessing Project Delivery
The objective of this section is to assist in assessing the viability of delivering the project for implementing an IT system. This is documented in the Viability Assessment work product.
Viability of Project Delivery is typically re-assessed at each phase of the project, The questions are intended to supplement those found in the Viability Assessment work product description. It provides a set of review questions that can help ascertain the completeness of the project estimates and delivery plan and point out common risk areas
## Assessment of the Project Scope
The goal of this step is to verify that the scope of work is clearly understood and the we have all of the planned information required to start the next phase (or continue the current phase) of the project.
Scope Documents
1. Do you have the proposal or SOW?
2. Are there any Change Orders to the SOW?
3. Do you have all the information the client is contractually required to supply?
4. Do you have sufficient output from previous project phases to allow you to proceed at this time?
5. Are the assumptions documented in the SOW and Change Orders still valid?
6. Do you have client approvals/acceptance of work completed in previous phases?
7. Is there any other client specific activity that could impact the project? E.g. account specific changes such as a pending move of location etc.
Partner Agreements
1. Do you have any subcontractors or global resources on this project?
2. Do you have the subcontractor/DOU agreements?
Solution Overview
1. Do all parties involved understand the solution?
2. Are the deliverables clearly defined and understood by all parties?
3. Is the acceptance criteria for the deliverables clearly defined?
4. Do all parties understand their roles and responsibilities for delivering the solution?
5. Are the organizational impacts of the solution understood and accounted for in the plan?
Technical Delivery Environment
1. Has the project delivery environment(s) been put in place for the customer, subcontractors, global resources and on-site team?
2. Are communication tools identified and tested?
## Assessment of the Project Work Estimates
The goal of this step is to verify that the scope of work is understood and included in both the financial estimate and the delivery project plan. This step should be repeated at each phase of the project or as often as significant new requirements are identified.
Work Areas
1. Are all in scope work areas included in the estimate?
2. Are non-function requirements considered in the estimate?
3. Is the work-breakdown structure sufficiently detailed?
4. Are all the deliverables identified and specified?
5. Are skills and responsibilities clearly identified?

Estimating Skills
1. Was the estimate prepared by people with appropriate estimating skills?
2. Was the estimate prepared by people with experience in the industry or application area?
3. Was sufficient time spent in preparing and generating the estimate?
Estimating Process
1. Who prepared the estimate?
2. Is there an estimate report?
3. Is the format of the estimate report in line with that recommended in the Project Control Book?
4. Has the methodology used been documented?
5. Were similar estimates/projects used to assist with the estimate?
6. Were the estimates checked during the generation process?
7. Is there a documented estimate validation?

Details Of The Estimate
1. Has the project been broken down into subprojects and an estimate produced for each?
2. Have all tasks for each subproject been identified and documented?
3. Were standard figures used to establish effort estimates for tasks?
4. Are the rates used appropriate in the circumstances?
5. Was appropriate scaling applied?
6. Does each subproject list:
  1. Deliverables?
  2. Assumptions?
  3. People, skills and availabilities?
1. Has adequate contingency been allowed?
2. Has allowance been made for effort over and above the project task work, such as:
- Project management?
- Set up and running of a project administration (project office)?
- Specialist support for guidance, technical review etc.?
- Assurance reviews?
- Progress reviews?
- Decision-making delays?
  Note: pricing the contract to a customer is a marketing decision. The focus of this paper is on estimating the scope of work, effort to complete the work and skill levels required to complete the work.

## Assessment of the Project Plan

Schedule and Plan
1. Have GSMethods and processes been applied correctly?
2. Have all factors and dependencies been allowed for in generating the schedule?
3. Has sufficient time been allowed for critical items?
4. Has time been allowed for:
- Project definition and startup?
- Establishing relationships with the business unit, the sponsor and with all external parties?
- Milestone or phase-end reviews and decisions?
Do plans cover:
Manpower—which skills are needed, and when?
- Management system—how the project will be managed?
- Reviews—how the project will be reviewed by management?
- Assurance—how project and technical assurance will be discharged?
- Testing—how the developing systems (business and IT) will be tested?
- Training—how project members and users will be educated and trained?
- Documentation—how project deliverables will be handled?
- Agreement—how approvals will be gained?
- Implementation—how the project and its deliverables will be handed over to the line business, and used as part of the day-to-day business activity?
1. Examples
2. References
Internet/intranet sites:
- Software Engineering Information Repository – https://seir.sei.cmu.edu/seir/
- Testing Methods & Practice Database on the ICM AssetWeb
- Tools – http://w3-5.ibm.com/transform/project/pmtoolsuite/
- Methods - http://w3-03.ibm.com/transform/project/pmtoolsuite/pmoview.html
Books, journals, articles:
- Software Engineering: A Practitioner’s Approach, Roger S. Pressman, McGraw Hill, 1997
- Handbook of Software Quality Assurance 3rd Edition, C. Gordon Schulmeyer/James I. McManus, Prentice Hall, 1998
Revision History
Revision Number	Revision Date	Summary of Changes	Author
Version 3.0	February 2007	Added new content: Business Requirements Assessment, Cutover to Production Assessment, Project Delivery Assessment	Pirooz Joodi, Beverly Bone
Version 2.1	November 2000	Applied new template and style, grammar and spell check.
Version 2.0	March 2000	Review Level 2: Document ready for client and Core Team review.
Version 1.4	March 2000	Review Level 1: Incorporate feedback from paper editors.
Version 1.3	March 2000	Review Level 1: Incorporate feedback from local SME team review.
Version 1.2	March 2000	Review Level 1: Document ready for official local SME team review.
Version 1.1	March 2000	Review Level 0: Incorporate feedback from Review Level 0.
Version 1.0	March 2000	Review Level 0: First draft ready for “pre-review” by local SMEs.

Revision History
Version 2.1 October 2000 – Removed confidentiality markings from header.
Version 2.0 September 1999 – New version created. Applied to template, spelling and grammar review.
Version 1.1 February 1999 – A standard format template was applied.
Version 1.0 September 1998 – Base version.