IBM Global Services

Architectural Methods of System Partitioning & Aggregation
Including Implications for Project Management

Whitepaper
© Copyright International Business Machines Corporation 2008
All Rights Reserved
Version 2.0, June 2014

Table of Contents

# Scope and Intent
The purpose of this guideline is to provide guidance on system partitioning best practice to architects and/or project/program managers working on large or complex service opportunities.
By employing this guidance when developing an IBM Solution, the architecture of the solution will provide the basis for an effective and efficient solution delivery plan.
This paper will cover:
- Identifying and applying best practice considerations to partition and aggregate elements of the proposed system
- Incorporating cross line-of-business and full lifecycle considerations into your solution design
- Mapping the partitions to an executable project plan
- Use of partitioning to (re-)confirm organizational assignments
- Validating the partitioning through a review process
Rather than provide the answers to specific problems, this paper provides a structured list of topics and considerations that should be leveraged when partitioning the system.
## Contact Information:
The following people contributed to this paper and can provide further information:
- Craig Rahenkamp (rahenkam@us.ibm.com)
- Adam Newth (adam_newth@uk.ibm.com)
- Brian R. Smith (brsmith@us.ibm.com)
- Mark Rhoades (rhoadesm@us.ibm.com)
## Revision History
Revision Number	Revision Date	Summary of Changes	Changes Marked?
Version 1.0	August 2008	Initial document creation	No
Version 2.0	June 2014	Updated to refer to and use the CSI Method Blueprint. Tidied up and simplified text breaking up paragraphs to make text easier to read and assimilate / Created a new section on the CSI Method Blueprint. / Re-worded many headings and introduced sub-headings in some chapters to make text and concepts easier to follow. / Consistent use of “Program” / “Program Mgr” / “Project” / “Project Manager” / Consistent use of “System Partition” (replacing or re-wording “Solution Partition”)

# Why Partitioning and Aggregation?
There are several reasons for focusing on the proper partitioning and aggregation of large systems: Some of them are practical from an architectural standpoint, some are driven by the way we conduct our services business, and others are driven by ongoing analyses of our project portfolio.
## Poor partitioning leads to troubled projects
One of the primary drivers behind the creation of this guideline was the trend observed by our quality assurance function, the Global GBS Delivery Excellence organization, during the years 2005 to 2013. Throughout this period, and continuing through 2014, many troubled projects were identified and reviewed. More than 50% of these projects were found to have proposed a system solution that was inadequately matched to the distributed development environment and implementation approach that was bid. In other words, the complexities of the project were not adequately addressed during solution design such that they could be managed effectively and efficiently during delivery.
## Partitioning drives the Project Organization and Plan
Many of our large, complex projects are simply too large for one Project Manager to manage all of the details. The key to successful management is structured delegation; breaking up a large program into multiple smaller projects or a large project into multiple smaller sub-projects that:
1. Can be packaged (as far as is possible) as complete self-contained efforts that produce end products or ‘configuration items’ that can then be integrated together into the complete solution.
2. Can be succinctly specified as to scope, requirements, interfaces, acceptance criteria, quality criteria, and interdependencies
3. Can be assigned to, and the day-to-day project management performed by, a single development organization (Global Delivery, subcontractor, other IBM service lines or lines of business) with acceptable risks
4. Have a governance structure in place at the top level of the program so that the constituent sub-projects can be managed as a portfolio of inter-related projects without having to have detailed day to day insight into each one. In other words, the status and reporting provide sufficient insight that knowledge of the details is only required on an exception basis.
As depicted below in Figure1, when properly executed, the decisions made in the development of the system architecture will drive the basic layout of the project management planning artifacts. The partitioning of the system into smaller pieces leads to the definition of smaller projects or sub-projects to design and build those pieces. So, the program or project manager must rely on (and work with) the technical leadership of the program to develop a system partitioning that makes sense from a complete lifecycle perspective.
This guideline aims to help you to partition a system so that it enables effective and efficient project management throughout delivery.

Figure 1: The System Architecture defines the structure of the project management artifacts
## Partitioning drives simplification and speed
Experience from successful projects tells us that partitioning a complex system drives simplification and speed;
Simplification: A large, complex problem may be much more easily solved by breaking the problem down into smaller problems. Even though this introduces a new technical risk associated with integration, the overall technical risk is reduced as it is easier to solve and manage a set of smaller problems than one large problem.
Speed: Once broken into smaller sub-problems, many of these smaller problems, if properly structured, can be solved in parallel so that the total end-to-end solution can be provided more rapidly. Speed is another way IBM can gain competitive advantage in the marketplace.
# System Partitioning in Context

## Partitioning in context of IT Architecture process
System Partitioning does not take place in a vacuum. It is an inherent part of the overall process of creating the IT architecture for a system.
This process starts with a (relatively) well defined set of top level requirements. These requirements are then analyzed in accordance with the architectural method selected.
The specific requirements modeling, architectural modeling, and analysis tools used by the different services lines, lines of business, and brands can vary significantly. It is expected that you will use the tools specific to the solution you are building. Examples of some of the various techniques involve the following:
- Use of Business Modeling Tools (e.g., Component Business Modeler [CBM]) to build the “heat map” – where the client needs to change.
- Use of Software Architecture Tools (e.g., System Architect [SA] and/or Rational Software Architect [RSA]) for building the high level system interactions and to refine the requirements – both at the system level and at the component level.
- Use of Business Process Modeling tools (e.g., Websphere Business Modeler [WBM] or Blueworks live or Business Process Manager/Process Designer [BPM/PD]) to build the specific business processes defined in RSA to do the CBM indicated business functions.
- Use of Service Oriented Architecture Tools/Techniques (such as SOMA) to model the services required by the system
During this process, insights will be gained into the components, functions, deployment units, and other aspect of the architecture. As these details become clear, the partitioning and aggregating of these elements into manageable chunks is enabled and becomes a core element of the project.
## Basic approach to partitioning
The basic approach for partitioning and aggregation is fundamental to architecting:
1. Decompose the problem into basic elements
2. Analyze the interactions between the elements
3. Aggregate the elements into logical groups or partitions (major architectural components)
4. Iterate – re-apply the analysis conducted to refine your solution (“stepwise refinement”).
Ensuring that all critical elements of the solution are taken into account is the only way to perform these steps effectively. By “all critical elements”, we are referring to not only what must be built, but how, by whom, and how all of the elements will be re-integrated, tested, and delivered to the client.
The challenges in partitioning and aggregation are primarily:
1. Finding the most suitable set of sub-problems, and
2. Combining the separate sub-problems into an overall solution (integration).
By following the best practice considerations for partitioning and aggregation, the difficulty of addressing these challenges will be reduced.
## The link between Architecture, Project Management, and Method
Throughout this guideline, we will tie the architectural implications to the project management discipline to drive home the importance of developing a project plan that maps to the solution the architect is developing
So that we have a conceptual ‘blank sheet of paper’, we will start with a generally applicable Work Breakdown Structure (WBS) that is based in complex systems integration project practice as defined in the Complex Systems Integration (CSI) Method Blueprint. This blueprint has been developed by GBS to provide a structure for organizing programs or projects that design and build large and complex solutions. Key concepts inherent in the CSI Method Blueprint are:
1. Large complex IT systems consist of many components (for example, traditional and/or agile applications, package applications, and infrastructure – both hardware and software)
2. Each component must fit within the constraints of the overall end-to-end (E2E) solution.
3. Individual components might follow different design / build / component test lifecycles as appropriate to the component.
4. Once components have been built and tested, they need to be integrated into the overall E2E solution for integration and system testing before being deployed.
We will discuss the CSI Method Blueprint more in section 4.5 when we consider method and delivery implications. The WBS that we will start with is represented in Table 1 below.
Table 1: Initial WBS Structure for a Complex Systems Integration program
1 ABC Finance Web Program / 1.1 Project Governance / 1.2 End-to-End System Level Engineering (Note: this includes things like System Level Requirements Engineering, Design, Development, Integration, Test, and Deployment) / 1.3 Critical Item Development (Major System Components) / 1.4 Infrastructure and environment design & development / 1.5 Organizational Change Management

# Partitioning Best Practice Considerations
The high-level list of system partitioning considerations is as follows:
- Use of classic architectural heuristics – applying ‘rules of thumb’
- Asset Use and Re-use – particularly, the use of off-the-shelf package applications
- End User Implications – splitting user components from functional components
- Development and Delivery Capability
- IBM Unified Method Framework Implications – selecting and combining IBM methods
- Integration & Test Approach- laying out how you will reassemble all of the partitions
- Deployment Considerations
We will consider each of these below. Note that while these considerations are being presented in series, in actual practice they are applied in parallel and/or in an iterative fashion, with constant trade-off analysis being conducted, so as to find a reasonably optimal partitioning.

## Architectural Heuristics
Heuristics are ‘rules of thumb’ that time and experiences have proven to be generally beneficial when employed. They are useful as a way of codifying lifetimes of experience or simple lessons learned.
Examples of classic heuristics include:
- Keep it simple, stupid (the KISS principle)
- Don't assume that the original statement of the problem is necessarily the best, or even the right one.
- Build in and maintain options as long as possible in the design and implementation of complex projects. You will use them. (This, in fact, forms a whole class of Risk Mitigation strategies).
- In partitioning, choose elements so that they are as independent as possible; that is, elements with low external complexity and high internal complexity (or cohesion).
- Group elements that are strongly related to one another. Separate elements that are unrelated.
- For a system to meet its acceptance criteria to the satisfaction of all parties, it must be engineered, designed, and built to do so, no more, no less.
- Define how an acceptance criterion is to be certified at the same time the criterion is established.
Exhaustive sets of heuristics can be found in the reference material cited at the end of this paper. Rechtin’s The Art of System Architecting contains many classics. In true recursive fashion, one must be smart in how one applies these heuristics. Kenneth Cureton, in his 1991 study, developed several heuristics for applying heuristics:
- Heuristics work best when applied early to reduce the solution space or solution complexity
- Knowing when and how to use heuristics is as important as knowing which ones and why
- If it works, then it's useful
- Strive for balance
- Remember, heuristics aren't reality, either
Most of our architects are trained in the application of heuristics to the architecting process. It is critical that they are applied to our large, complex deals.
Figure 2 below provides an example of the application of classic architectural heuristics. The example is a representative combination of elements based on an architect’s experience with web services and SOA, with some analysis done to logically group requirements and functions into partitions.
The distinction between the two applications, A and B, will be discussed in the next section. Of interest to the above discussion is the application of some of the above heuristics, as noted in red in the diagram.

Enterprise Services Bus (Message Broker / Middleware)
Web Services
Users
Existing Legacy Systems
Client Product Catalogue
Shipping System
Application B (Custom)
Application A (SAP)
SOA Registry
Services Broker
Supervisor

SAP SOA adapter

High internal complexity
Relatively simple, well defined interface. Good place to break the design into components
Highly complex interaction: keep together
Might have to put wrapper around these existing systems

Figure 2: Heuristics applied to a sample problem
If we were to then develop the project WBS based on the above preliminary architectural partitioning, it might look something like the WBS in Table 2 below.
The major development items include Applications A and B, which have been pulled out for reasons that will become clear shortly. The SOA and Web Services pieces have been grouped together as infrastructure elements for the time being.
Table 2: WBS based on initial partitioning
1 ABC Finance Web Program / 1.1 Project Governance / 1.2 End-to-End System Level Engineering / 1.3 Critical Item Development (Major System Components) / 1.3.1 Application A Critical Items / 1.3.2 Application B Critical Items / 1.3.3 Legacy System Interfaces / 1.4 Infrastructure and environment design & development / 1.4.1 Infrastructure critical items (to be refined) / 1.5 Organizational Change Management

## Asset Use and Re-use
The considerations of asset use and re-use revolve around the application of existing software assets, custom re-use libraries, and off-the-shelf software.
Package applications such as SAP, Oracle, DB2, and Siebel are classic examples of off the shelf software, as is Open Source software. Custom re-use libraries are not as common, but in some application development shops, they are essential to lowering production costs.
If re-use is being considered, structure the system architecture to take good advantage of the packages. In other words, try to group the requirements so that those things that the package does well fall into a partition wherein that package can be employed. Place requirements that are not related to the package capabilities in other partitions.
Note that some requirements may span several partitions, and there must be a plan to deal with them. In Figure 2 above, application A is shown to be the combination of a package (SAP) plus some SOA adaptors.
In this example, some requirements, primarily related to the interfaces, have been placed in the package partition, even though SAP may not be able to handle them natively. Due to the high degree of interaction between the SOA adapter and SAP, they are left in one partition.
Interfacing to packaged applications (e.g., SAP, Seibel, and others) can be a problem area. Many package application deals get sold with nearly all “out of the box” functionality – only to discover that the interfaces to existing systems is so complex that it requires a complex SI approach to integrate completely.
One must pay close attention to how assets must interface to the rest of the system – and the legacy system(s) – so that the project can be properly partitioned and sized.
As stated in the last section, strive for balance. Breaking down an architecture based only on application capabilities can be detrimental if the other design elements are not taken into consideration.
## End User considerations
End Users are a special group of stakeholders. In a web application, they may be the general public. If they are application users internal to the client (e.g., help desk operators, sales staff, financial staff), then they may be accustomed to certain corporate standards or terminology relative to IT systems. The maintainers and operators are yet other classes of potential End Users.
In the context of partitioning, the main consideration is to determine if it is possible to group external user interfaces from various elements of the system into a common partition where consistency in style, terminology, standards, and practices can be employed and enforced. Grouping all user interfaces into a single partition may be acceptable for some systems. For complex systems, it may it be more efficient to put the user interfaces into several partitions. For example, define separate partitions for:
- a web interface to the public at large,
- a dedicated service provider interface for help desk operators, and
- yet another set of interfaces for the operators and maintainers actually hosting the application,

Putting the user interfaces in partitions separate from the more functional aspects of the system enables the User Interface to be built using a different development lifecycle from the main application. For example, the User Interface might be built using agile or accelerated development methods (Agile, Spiral, or Iterative), whereas the main application might be built using a more traditional development lifecycle.
As the early requirements around the user interface are typically less well understood than some of the functional requirements, proposing to the client a rapid prototyping approach to the user interface will let them focus on the usability aspects early in the program, leading to better client satisfaction, less rework later in the development cycle, and lower risk for the project.
This is reflected in Figure 3 below, and in Table 3, which shows the infrastructure critical item element broken down to include SOA, Enterprise and Web services and User Interfaces.

Enterprise Services Bus (Message Broker / Middleware)
Web Services
Users
Existing Legacy Systems
Client Product Catalogue
Shipping System
Application B (Custom)
Application A (SAP plus SOA adapters)
SOA Registry
Services Broker
Supervisor

User Interface

Figure 3: End User Considerations
Table 3: WBS with end users and infrastructure considered.
1 ABC Finance Web Program / 1.1 Project Governance / 1.2 End-to-End System Level Engineering / 1.3 Critical Item Development (Major System Components) / 1.3.1 Application A Critical Items / 1.3.2 Application B Critical Items / 1.3.3 Legacy System Interfaces / 1.4 Infrastructure and environment design & development / 1.4.1 Infrastructure critical items / 1.4.1.1 SOA Core / 1.4.1.2 Enterprise Services Bus / 1.4.1.3 Web Services / 1.4.1.4 User Interfaces (note: may including prototyping) / 1.5 Organizational Change Management

## Development and Delivery Capability considerations
The specification of system partitions needs to consider the ability of the development and delivery organizations to perform the work needed to deliver a particular partition.

Effective Delegation
In Complex Systems Integration delivery, there are a lot of details to manage. The key to managing the details, both from a project management and technical leadership perspective, is to delegate effectively. During partitioning, specifying separate but whole elements of the system, where each has clearly defined requirements, interfaces, quality criteria, and acceptance criteria, is the first step to achieving this.
Couple this partitioning with sound project management practices, such as detailed planning and scheduling, project reviews, inspections, escalation, periodic cost & schedule reporting, and status reporting - all of which contribute to a set of leading performance indicators - completes the approach.
This allows the PM or Chief Architect to focus at the top level of the system development and to attend to issues in each partition as the leading indicators warrant.

In our large and complex projects, we frequently deal with multiple development or delivery organizations:
- the client’s Information Technology (IT) group,
- GTS or GBS Service Line delivery resources,
- IBM’s global delivery centers,
- other IBM organizations / lines of business,
- and external service providers (subcontractors).
The goal is to find the optimum delivery organization for each partition and to affirm that the division of partitions is acceptable from this delivery perspective.
As each partition is assessed, the team should consider the potential candidates for developing that part of the system.
The candidate team’s skills, capability, and experience should be evaluated along with the prime organization’s ability to manage (interface with, communicate with, and have oversight into) that candidate team.
The main decision criteria should focus on technical capability, cost and risk.
The partitions should be specified so that, as far as possible, each development and delivery organization is self-contained and supplying a whole, separate and testable function or critical item. This will allow each development team to work independently, in parallel, and best exploit the skill base of the team. See the box at right on effective delegation.
During delivery, each supplier (be it IBM, the client, or a subcontractor) should then be responsible for assigning work within its own team and managing its own delivery.
 For development or integration contracts, avoid the “staff augmentation” approach (also known as “services to support”).
A final consideration when reviewing partitions is to minimize the number of suppliers any single part of the system goes through before it reaches final integration. For example, a piece of software should go through ideally one, (but at most two) other organization(s) before it reaches the final integration.
During this analysis, it may become apparent that, due to skills, specialization, integration sequencing, risk, or other factors, some redrawing of the partitions may be needed.
The analysis may also reveal that the organization that is best positioned to do the work requires some retooling or additional training before becoming truly proficient at the work to be done. In these cases, the start-up costs and/or training curve must be accounted for by appropriate adjustments to cost and schedules.
Some thoughts on organizational considerations relative to the example problem are depicted in Figure 4 below. Due to the nature of the preliminary partitioning, there are no effects on the partitioning of our example at this point. As such, there is no impact to the WBS presented in the previous section.

This is a good candidate for the GBS AIS Portal team

Enterprise Services Bus (Message Broker / Middleware)
Web Services
Users
Existing Legacy Systems
Client Product Catalogue
Shipping System
Application B (Custom)
Application A (SAP plus SOA adapters)
SOA Registry
Services Broker
Supervisor

User Interface

This is a good candidate for the India GDC that specializes in SAP
This is may be a good candidate for a software factory (GBS AIS)

Figure 4: Development Capability considerations
## IBM Unified Method Framework Considerations
Upon examination, the example problem in Figure 4 does not fit well into any single ‘method’ within IBM’s UMF. As shown in Figure 5 below, there is the potential for using AD 2.0, any of several SAP delivery processes, Agile with Discipline, and many other delivery processes. The selection of any one of these delivery processes over the others would result in a mis-match of work products, tasks, and/or activities that would be extremely difficult to manage effectively, if at all.
There are two interrelated sets of considerations to be made relative to IBM’s Unified Methods: 1) For each partition of the program, the selection of the best method to be used in the development of that partition, and 2) the method to be used for the overall integration of the partitions into the completed system level solution. As the latter has some implications as to how to tailor the former, an overview of IBM’s Complex System Integration Method Blueprint is first provided to give the reader some background.
### Employing the CSI Method Blueprint
As described in section 3.3, The Complex Systems Integration (CSI) Method Blueprint has been developed by GBS to provide a structure for organizing projects that design and build large complex IT systems. The CSI Method Blueprint is published in the IBM Unified Method Framework along with training material so it is easy to apply. The diagram below provides a 1-page view of the End-to-End Delivery Model for Complex SI programs.

The recommended approach for large complex systems integration projects is
1. To use the CSI Method Blueprint to provide the overall ‘structure’ for organizing the overall design, build, integration, test, and deployment of the end-to-end solution.
2. Within the structure provided by the CSI Method Blueprint, to use individual delivery processes appropriate to the design, build, and test of each partition of the system.
A Method Adoption Workshop should be held to adopt the overall method for the whole project and E2E solution. A MAW is a construct in which the method is tailored through the adoption of work products that need to be created and the selection of activities and tasks necessary to develop those work products.
### Identify the best-fit ‘method’ for each partition
Assuming the application of the considerations to this point has been done appropriately, the partitions should, individually, reflect a single project (or sub-project). Each project may have dependencies on others relative to interfaces or data, but these boundary conditions should now be well specified and controlled.
Further, the content of each partition should be relatively homogenous. This homogeneity may point to a preferred method for each partition. Figure 5 is a good example of the self-evident nature of the methods applicable to some of the partitions.
Unfortunately, some partitions may not reflect an obvious, or indeed, any method, as the best selection. In the real world, the organizations believed to have the skills necessary to build the partitions are frequently brought in to recommend and tailor the method(s) best suited for these partitions.
In the example of Figure 5, the wrappers, MQ Series, and/or SOA Adapters necessary to interface the exiting legacy systems to the ESB may not fit cleanly into any of the existing methods, with the possible exception of AD 2.0.
If there is a significant amount of data that must be manipulated or modified for the solution to properly function in the target environment, then Data Migration activities must be integrated into the activities and tasks associated with the partition.
### Tailor Individual Methods for each partition
Once the methods for each partition have been identified, they must be tailored to the content. This can be done using a reduced-scope method adoption workshop, or “mini-MAW”. Maws were discussed briefly in section 4.5.1 above.
Mini-MAWs can be held in parallel if there is a one-to-one mapping of delivery organizations to partitions. This may not be possible when there is more than one organization involved, or when the prime organization (the one responsible for overall integration) wants to be involved in each of the mini-MAWs. The process for conducting a MAW is well defined in the method (See references at the end of this paper).
### Specify the method for integrating partitions into the E2E Solution
This step is to ensure that all of the partitions come back together into an integrated solution at the appropriate time in the development cycle.
The process for sequencing the integration will be addressed in the next section; however, the identification of what has to be done, from a methods perspective, is described here.
The selection of an overall integrating method must be made or, in some cases, synthesized from existing methods that are “close enough”. There are two aspects to this:
  1. integration of the development cycle, so that the program (a collection of parallel projects) can be managed by the prime organization, and
  2. the integration of the output of the parallel projects (working code, subsystems, platforms, facilities, and/or data) into the final solution that meets the client’s needs and requirements.
Both of these aspects are handled within the CSI Method Blueprint E2E Delivery Model which is the overall framework recommended for large complex projects.
The CSI Method Blueprint uses the Systems Engineering (SE) Phase Reviews as a common client-oriented qualitative and quantitative set of check-points at the end of each significant phase of the integrated project.
By identifying these SE checkpoints, or milestones, at the top level of the delivery plan and driving them into the delivery method for each partition, there is a unifying structure that can be used by all delivery organizations and the client. These checkpoints provide consistent insight and assessment into technical, risk, cost, and schedule aspects of the project.
There are other aspects of the solution that may have to be explored due to the nature of the engagement. Subject areas like security, privacy, and high availability systems (banks and transaction systems) can be overlooked if they are not included in the partition-unique methods. The topics mentioned all have their own methods in UMF. These methods should be reviewed for applicability by looking through the list of work products and deliverables. Should any of these be found to be applicable, the appropriate task/activities should be pulled from those methods and integrated into the WBS structure. See Table 4 for a suggestion on how to treat these in the WBS.
The second aspect of integration is combining the piece parts that come out of these separate projects into the integrated solution for the client. There are several methods that can be selected or tailored to provide this structure, including the System Lifecycle Framework (SLF), AD2.0, Data Center Transition, Infrastructure Testing, Rollout Services, the Test Family Core Method, and Test Strategy and Planning. It is likely that no one of these provides all of the work products, tasks, or activities necessary for a complex SI program. Instead, a unique approach will be synthesized based on the sequencing of events (covered in the next section) and then picking the correct Work Products, tasks, and activities from one or more of these methods.
One last consideration, more related to methods than to partitioning, is identified here, but discussed in a later section. Nearly all of our projects get deployed at some point in time. In order for the client to be able to receive the solution and start to operate and employ it, there is typically some effort expended to ready the client facilities and the client employees for the transition. There are methods in UMF to help define these activities and they should be evaluated in producing the final WBS. The architects, consultants, and/or project (or proposal) manager should be involved in this selection and tailoring, as it takes technical insight the PM typically does not have. This part of the technical project planning, however, rarely has any influence on the partitioning.

Enterprise Services Bus (Message Broker / Middleware)
Web Services
Users
Existing Legacy Systems
Client Product Catalogue
Shipping System
Application B (Custom)
Application A (SAP plus SOA adapters)
SOA Registry
Services Broker
Supervisor

User Interface

Ascendant SAP or Ascendant SAP Global Delivery
AD2.0 or AwD
AD 2.0
AwD?
IBM Portal Services? AD2.0?

AD 2.0? Data Migration? IMUM?

SOMA Complete or AD 2.0
Figure 5: Method Considerations
Table 4: WBS with Method Implications.
1 ABC Finance Program / 1.1 Project governance / 1.2 End-to-End System Level Engineering / 1.3 Critical Item Development (Major System Components) / 1.3.1 Application A Critical Item (based on SAP) / 1.3.1.1 Market Initiation / 1.3.1.2 Solution Preparation / 1.3.1.3 Business Blueprint / 1.3.1.4 Realization / 1.3.1.5 Cluster Preparation / 1.3.1.6 Cluster Go Live to Sustain / 1.3.2 Application B Critical Item (based on AD 2.0) / 1.3.2.1 Solution Outline / 1.3.2.1 Macro Design / 1.3.2.1 Micro Design / 1.3.2.1 Build Cycle / 1.3.2.1 Deployment / 1.3.2.1 Solution Close / 1.3.3 Legacy System Interfaces / 1.4 Infrastructure and environment design & development / 1.4.1 Infrastructure Critical Items / 1.4.1.1 SOA Core (SOMA Complete) / 1.4.1.1.1 Start-up	1.4.1.1.2 Model / 1.4.1.1.3 Assemble / 1.4.1.1.4 Deploy / 1.4.1.1.5 Close / 1.4.1.2 Enterprise Services Bus (SOMA) / 1.4.1.2.1 Start-up / 1.4.1.2.2 Model / 1.4.1.2.3 Assemble / 1.4.1.2.4 Deploy / 1.4.1.2.5 Close / 1.4.1.3 Web Services (Portal Services) / 1.4.1.3.1 Engagement Start-up / 1.4.1.3.1 Solution Definition / 1.4.1.3.1 Macro Design / 1.4.1.3.1 Micro Design / 1.4.1.3.1 Build Cycle / 1.4.1.3.1 Deployment / 1.4.1.4 User Interface (Agile with Discipline) / 1.4.1.4.1 Inception / 1.4.1.4.2 Elaboration / 1.4.1.4.3 Construction / 1.4.1.4.4 Transition / 1.5 Organizational Change Management
Notes on this WBS: / This represents the first cut at adding detail. Many aspects of the design must take place at the system level, and these are not yet reflected. Some elements of the methods in the partition must/will be pulled up to the system level (e.g., system level design (including SOA implications), integration planning, test planning, deployment planning, organizational change management, integration, test, deployment, and transition). / The Systems Engineering Capability Pattern reviews would be inserted into the partition methods as appropriate. For example, the Preliminary Design Review would be conducted at the end of solution preparation (SAP), Macro Design (AD 2.0 and Portal Services), Model (SOMA), and Inception (AwD). As this phase-ending milestone is one of the activities within those phases, that level of detail is not shown.

## Integration & Test Considerations
As mentioned in the introduction, breaking a complex project or proposal into sub-problem domains will solve many problems. However, it also introduces new ones - especially when combining the separate subsystem solutions back into an overall solution.
Careful review must be made so that no gaps or side-effects are introduced in to the overall proposed solution. If side-effects are introduced, ensure they are appropriately addressed.
The first consideration is determining how the components and elements of the system will be integrated.
Approaches such as waterfall, sequential, iterative, big bang, and parallel operations all have their places, strengths, and weaknesses, but one (or more) must be selected and tailored for the set of partitions identified. A sequential approach is described next, while an iterative approach will be discussed at the end of this section.
Whether one chooses either of the two integration approaches discussed below, a blend of them, or one of the other integration approaches listed at the beginning of this section, the key is to understand the impact the approach has in how the work is partitioned, how it is planned, and how it is controlled during contract execution. Some of these methods are better suited to global distribution of responsibility than others, but nearly any of them can be made to work
### Example 1: Sequential Approach to Integration
The first step of integration to be considered is the acceptance of each partition before it arrives at the integration process. As the team refines the requirements of each partition, identify how it should be tested for compliance and meeting acceptance criteria. Consider whether special test data or equipment will be needed by the supplying development organization. If special testing needs are identified, determine who will provide the data or equipment (see Figure 6 at right). Document both the need (requirement) and responsibility so that it can be included in the WBS and effort estimates.

Interface Driver (unique test SW)
Application A (SAP plus SOA adapters)

I/F driver should be able to test all message types and provide both nominal and degraded mode stimulus.

The second step of integration to be considered is the sequencing of events. This includes understanding the needs for the integration environment(s) and the testing environment(s) necessary to support the integration of the partitions being proposed. This includes both the ‘hooks’, or connections, in the software used for testing purposes and the interface considerations – both external and internal - used by the solution.
As in the acceptance of the individual partitions, the needs for special test equipment and test data during integration must not be overlooked.
Figure 6: Partition Acceptance Testing
Figure 7 below provides some insight into these considerations. The figure depicts the first application (Application A) being tested in the integration environment. In order for the testing to take place, several prerequisites must have preceded it. Specifically, the integration of the SOA elements, the enterprise services bus, the web services, and the user interface must occur before we can start adding applications into the environment.
The determination of these prerequisite activities is essential in determining the sequence of the integration. Following this logic further, once application A is integrated, each of the interface drivers depicted at the bottom could be individually replaced with the real interface (for testing purposes) in sequence, then Application B could then be introduced and integrated.
This is just one sample sequence – the one selected will be driven by risk and the schedules of the larger partitions. The point with this approach is to maintain control over the integration environment and minimize the risk of integration failure: introduce only one new unknown into the environment at a time. As before, be sure to note the requirements for special test software and special test data to support the integration approach selected.
This partition integration concept can be visualized in a schedule format as depicted in Figure 8 – a Gantt chart depicting the integration sequence. The top half of this graphic represents the unit or component acceptance testing that is embedded in the partition methods, while the bottom half represents unique system level integration tasks and activities that must be accounted for in the WBS. Table 5 below depicts how this approach is depicted in the integration portion of the WBS.
System level testing, the final set of functional and non-functional testing conducted on the fully integrated system prior to putting it into a production environment, typically does not have a significant impact on the partitioning. The focus of this test is across all partitions, so, for this test to be conducted, all elements of the system must have been integrated and ready for testing. Assuming full consideration for the integration process has been incorporated into the plans, the system level testing should be straight forward.

Enterprise Services Bus (Message Broker / Middleware)
Web Services
User I/F Scripts Scripts
Legacy I/F Driver Unique Test SW

Catalogue I/F Driver Unique Test SW

Shipping I/F Driver Unique Test SW

Application B I/F Driver Unique Test SW
Application A (SAP plus SOA adapters)
SOA Registry
Services Broker
Supervisor

User Interface

Figure 7: A Step in the Integration Process

Figure 8: The integration sequence captured in a Gantt chart
Table 5: WBS reflecting integration considerations
o o o / 1.2 End-to-End System Level Engineering Activities / 1.2.1 Business and System Level Requirements / 1.2.2 Integration and test planning / 1.2.2.1 Integration and Test Planning / 1.2.2.2 Special integration and test software, data, and equipment specification / 1.2.2.3 Integration and test preparation (build test cases, environments, special test software & data) / 1.2.3 System Integration / 1.2.3.1 User I/F and Services Integration / 1.2.3.2 Enterprise Service Bus Integration / 1.2.3.3 Application A Integration / 1.2.3.4 Legacy I/F Integration / 1.2.3.5 Catalog I/F Integration / 1.2.3.6 Shipping I/F Integration / 1.2.3.7 Application B Integration / 1.2.4 System Test / 1.2.5 Deployment / 1.3 Critical Item Development (Major System Components) / o o o

### Example 2: Iterative Approach to Integration
An iterative approach to integration, such as Spiral or Agile, allows integration to be accomplished in parallel with the development efforts. While this has the benefit of potentially lower risk during the final integration, it comes at the price of more coordination being required within the development planning for each partition.
To be specific, each partition that is to participate in the iterative integration must first concentrate on the infrastructure their partition will use for interfacing and interacting with the environment.
- In the AD 2.0 world, this would be the interface drivers, interrupt processing, data access processes, and other basic services necessary for the bulk of the code to accomplish their functionality.
- In a SOA based project, this would be the Enterprise Service Bus, SOA Registry, the Services Broker, and the SOA Supervisor, along with the appropriate modules in each of the application partitions.
The intent in the early iterations is to get the basic infrastructure working and talking together, then add more of the application functionality in later iterations.
In order to ensure that the partitions will work together in each iteration, the goals of each iteration must be established up front, with the appropriate requirements and design elements assigned to (and completed in) specific iterations for each partition.
One does not have to plan all of the details for every iteration at the beginning of the project.
The classic application of Spiral requires full detail for the first iteration only, a little less for the second (for example, maybe 80-90% of the second iteration is planned, with 10-20% allotted to rework of bug fixes from the first iteration), and a monotonically decreasing amount of detail for each successive spiral, until the last one or two iterations, which may contain few placeholders for content, are primarily reserved for final rework, performance tuning, and bug fixes.
When using this approach, note that the establishment of an integration environment must occur much earlier in the program than would the incremental approach described above. The spiral (or Agile) approach allows each successive iteration to be adapted to lessons learned from the previous iteration. In addition to lower integration risk, this method allows early insight into system and network latency, potentially reducing the risk in meeting non-functional performance requirements as well.
.
## Deployment Considerations
The deployment of a complex system can vary significantly based on its physical and functional nature.
Installing Point-of-Sale systems into 3000 retail establishments around the globe will have a significantly different deployment plan than would either a web-based retail site or a transaction processing system in a bank.
In addition, most of our clients are very averse to risk when we are dealing with their core business systems. These realities will cause consideration of various deployment techniques;
- “big bang” (put everything in place and throw the switch)
- “gradual roll-out” of new system
- “incremental replacement” of legacy components,
- “parallel running” of new system alongside with the old business systems until the client is ready to shut down the old systems.
IBM’s architecture best practice calls for the identification of deployment units in the earliest stages of system design.
As such, these units should be well reflected in the partitions that were initially drafted early in this process. If this is not the case, one should review the partitioning in light of the deployment approach identified for the project. Any re-partitioning or subdividing of existing partitions should be evaluated using all of the considerations identified in this guideline.
One should also review IBM’s Unified Method for deployment considerations. The Rollout Services method in particular provides some guidance in planning this aspect of a project.
Close interaction with the client during the planning of this phase of the project is especially critical, as it may identify additional training, timing, and or staffing requirements associated with the client’s workforce.
Coordination of the client’s responsibility with that of IBM is required for a successful deployment.
## Integrating the IBM Lines of Business (LoB’s)
The IBM delivery team for large complex projects usually consists of multiple lines of IBM business. Once an initial view of the system partitioning has been developed, an additional step is needed to make sure that the IBM lines of business can present a unified delivery.
IBM’s lead architect from the prime (lead) organization must work with the technical leads from each line of business involved in the project. It is critical that the technical leads have a common understanding of the delivery of the solution. In addition to a common understanding, all requirements for each partition that is owned by a different line of business need to be properly documented and agreed upon.
If the solution includes a hosting environment, make certain the requirements are well defined and properly allocated to the partitions (e.g., both the hosting partition(s) and the application development partition(s)) and to have the roles and responsibilities of both parties clearly laid out. In most cases involving IBM hosting, the IBM standard hosting environment(s) will dictate additional requirements on the application software to be hosted.
The lead architect should make certain that all the requirements for the end-to-end solution are covered and that there are no gaps in understanding. There must be clear agreement of roles and responsibilities across the lines of business
The lead IBM project manager role is to work with the technical team to identify requirements, interdependencies, and any unique touch-points needed for the solution. The project manager will document all responsibilities across the lines of business in DOUs (documents of understanding).
## Technical Management and Program Level Design Control
Once the architectural breakdown is complete and signed-off by the program’s technical authority (for example, a design authority set up for the proposal or project), it is used as the basis for the project management plan (the WBS, etc.).
Even so, one must plan for program realities: the partitioning of the system will change so, just as the project schedule, costs, and reporting must be managed throughout the project life cycle, so must the technical solution.
Changes will come from many sources, both internal and external. Some of the changes will impact the interfaces between partitions, some may impact the integration effort, and some may add new requirements across all partitions.
Since the development work for these partitions has been delegated to development organizations around the globe, these changes must be centrally assessed and approved, then appropriately allocated out to all of the affected organizations in a timely, efficient, and controlled manner.
This Technical Management and Program Level Design Control must be accounted for in the project plans. It is more than just ‘project management’: it is the intellectual control of the architectural and integration aspects of the program. It should have a change assessment process, a change control process, and continuous insight into the development and integration activities (for example, those individuals performing in this capacity should have an ongoing role in the regular status and review sessions for each of the suppliers).
The CSI SEMP Template in UMF provides an excellent starting point for defining Technical Management activities
This area is the last of the technical best practice considerations that should directly influence the work breakdown structure. The activities that are involved in the ongoing management and intellectual control of the architecture, design, and integration and test approach and plans must be included in the WBS so that the activities may be estimated, scheduled, and priced. Table 6 has a notional representation of some of these activities embedded under the Technical Governance activities.
As this technical control spans the entire end-to-end solution, it must be at the solution level and not constrained within any one partition.
Many of these activities come from the technical management plan or the systems engineering capability pattern. The actual entries should reflect the content of the system and approach being planned.

Table 6: WBS reflecting technical governance activities
1 ABC Finance Web Program / 1.1 Project Governance / 1.1.1 Project management / 1.1.2 Technical Management and Design Control / 1.1.2.1 Establish Customer Baselines / 1.1.2.2 Design Authority / Technical Change Control / 1.1.2.3 Technical Environment planning & execution / 1.1.2.4 Technical Reviews / 1.1.2.5 Risk Mitigation / 1.2 End-to-End System Level Engineering Activities / o o o

# Evaluating the partitioning: Did we meet our goals?
At this point the IBM proposal team has defined the IBM Solution and knows what to build in terms of a set of system partitions, how each partition will be built, and how the partitions will be integrated together into the overall end to end solution.
It is now time to review and evaluate the system design and partitioning to assess whether it is a viable solution for achieving the project goals.
Viability is typically re-assessed multiple times during the life of a project. A separate IBM guideline is available to provide additional guidance assessing viability (see the reference material cited at the end of this guideline).
To determine the viability of the proposed partitioning, the team should answer these questions about the business requirements, solution design, data migration, cutover to production and project delivery:
- Are the business requirements mapped to the scope of the project?
- Are the requirements traceable to the architecture?
- Are the requirements and external interfaces completely covered and allocated across the partitions?
- Are there clear interfaces / boundaries between the partitions?
- Does the partitioning provide for complete project estimates and delivery plan?
- Does the definition of the partitioning provide the basic information which will allow the technical designs, both logical and physical architectures, to be complete and agreed upon?
- Are there minimum interdependencies between partitions during development?
- Does the partitioning preclude future system enhancements? In other words, does the partitioning allow for extensibility, i.e., accommodates system growth and introduction of new technologies?
- Does the partitioning provide enough detail in order to communicate the solution to the client and the delivery organizations responsible for implementation?
- Are the partitions defined sufficiently so that the assigned delivery organization can plan for and accurately estimate the effort to deliver its partition?
- Are the partitions using the right methods, and does the integration of the partitions into a whole system use the CSI Method Blueprint?
- Is the IT system (and each system partition) deliverable within the constraints of time, customer capability, budget, available knowledge and skills, and other resources?
- Are the production cutover plans achievable and compete? Is there a checklist for verifying the cutover steps?
- Are the risks assessed?

When reviewing the above questions, if any are answered no by the project team, the areas of concern should be investigated and appropriate action taken to make sure the goal is met.

# References
## Textbooks

Beam, Walter R. Systems Engineering: Architecture and Design. New York: McGraw-Hill, 1990.
Blanchard, Benjamin S., and W. J. Fabrycky. Systems Engineering and Analysis. Upper Saddle River, N.J.: Pearson Prentice Hall, 2006.
Blanchard, Benjamin S. System Engineering Management. New York: Wiley, 1998.
Eisner, Howard. Essentials of Project and Systems Engineering Management. New York: Wiley, 2002.
Kossiakoff, Alexander, and William N. Sweet. Systems Engineering: Principles and Practices. Wiley series in systems engineering and management. New York: J. Wiley, 2003.
Maier, Mark, and Eberhardt Rechtin. The Art of Systems Architecting. Boca Raton: CRC Press, 2000.
Martin, James N. Systems Engineering Guidebook: A Process for Developing Systems and Products. Boca Raton, Fla: CRC Press, 1997.
Sage, Andrew P., and William B. Rouse. Handbook of Systems Engineering and Management. New York: Wiley, 1999.
Sage, Andrew P., and James E. Armstrong. Introduction to Systems Engineering. New York: Wiley, 2000.
Stanley, C. Maxwell. The Consulting Engineer. New York: Wiley, 1982.
Stewart, Rodney D. Cost Estimating. New York: Wiley, 1982.
Westerman, H. Robert. Systems Engineering Principles and Practice. Boston: Artech House, 2001.
INCOSE Systems Engineering Handbook: Version 3.1. [S.l.]: INCOSE, 2007. (IBM employees can get a free download at this LINK)
## IBM Resources
Leading Large Services Opportunities	Craig Rahenkamp et al.
The Complex SI Estimating Wiki
The Complex Program Management Community
The Complex Systems Integration Community
The IBM Systems Engineering Community of Practice
Architectural thinking education class
Systems Engineering Management Plan (UMF)
Complex Systems Integration (CSI) Method Blueprint (UMF)
IBM Complex Project Management	IBM training course.
Multi-National Project Management	IBM training course.